## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Construction of pathway, surface drain and chatal, installation of paver block, land development along with the others allied works at Samuktala Zone-I head work site PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000197/2023-2024 | 1495/ALD | 16/08/2023 | 15/10/2023 | DIPAK DAS | 13.04 | 0 | 0 | 0
2 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Construction of excess work of Boundary wall & 3m Span open Foundation Culvert with Boulder Protection works and other alied works at 2nd Site of Samuktala PWSS Zone-I PWSS Alipurduar Sadar Sub-Division, under Alipurduar Division PHE DTE. (SM/12561) | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000228/2024-2025 | 2281/ALD | 05/08/2024 | 04/10/2024 | PRITAM DAS | 12.58 | 0 | 0 | 0
3 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Construction of 100cum. OHR for SAMUKTALA ZONE-III Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000265/2022-2023 | 1658/ALD | 19/09/2022 | 18/03/2023 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 43.9 | 21.25 | 48.41 | 66
4 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Soil investigation work at 3 different places of Samuktala within Alipurduar District under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000266/2022-2023 | 1657/ALD | 19/09/2022 | 19/10/2022 | ASIS ENTERPRISE | 3.65 | 3.65 | 100 | 50
5 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Construction of Boundary wall at 3rd TW site of Samuktalata PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000267/2022-2023 | 1666/ALD | 19/09/2022 | 19/10/2022 | PRITAM DAS | 4.74 | 4.74 | 100 | 47
6 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Construction of Boundary wall at 5th TW site of Samuktalata PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000268/2022-2023 | 1668/ALD | 19/09/2022 | 17/04/2023 | ROY & PANDIT CONSTRUCTIONS | 4.76 | 4.13 | 86.72 | 100
7 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Construction of Pump House at 1st TW site of Samuktalata PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division |  | ORD/000269/2022-2023 | 1669/ALD | 19/09/2022 | 18/11/2022 | KOUSHIK BHOWMICK | 4.77 | 3.88 | 81.45 | 95
8 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Construction of Pump House at 3rd TW site of Samuktalata PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division |  | ORD/000270/2022-2023 | 1671/ALD | 19/09/2022 | 18/11/2022 | SWADESH DEV | 4.75 | 4.65 | 97.97 | 100
9 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Construction of Pump House at 4th TW site of Samuktalata PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000271/2022-2023 | 1672/ALD | 19/09/2022 | 18/11/2022 | PROJIT HALDER | 4.77 | 0 | 0 | 0
10 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Construction of Pump House at 5th TW site of Samuktalata PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000272/2022-2023 | 1673/ALD | 19/09/2022 | 18/11/2022 | CHITTA RANJAN DEY | 4.75 | 2.35 | 49.46 | 100
11 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Construction of Boundary wall at 4th TW site of Samuktalata PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division |  | ORD/000273/2022-2023 | 1667/ALD | 19/09/2022 | 03/11/2022 | DHANENDRA SARKAR | 4.77 | 4.74 | 99.47 | 100
12 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Construction of 400cum OHR for SAMUKTALA ZONE-I Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000274/2022-2023 | 1659/ALD | 19/09/2022 | 18/03/2023 | DILIP MAHATO | 77.32 | 72.8 | 94.16 | 100
13 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Construction of 350cum OHR for SAMUKTALA ZONE-II Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000275/2022-2023 | 1661/ALD | 19/09/2022 | 18/03/2023 | MATARA CONSTRUCTION CO | 71.41 | 60.8 | 85.14 | 100
14 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Laying Distribution pipe with DI and UPVC pipe of SAMUKTALA ZONE-II WSS under Alipurduar Division, PHE Dte. (Part-A) | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000276/2022-2023 | 1662/ALD | 19/09/2022 | 18/03/2023 | M/S SSB CONSTRUCTION CO. | 100.42 | 92.48 | 92.09 | 48
15 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Laying Distribution pipe with DI and UPVC pipe of SAMUKTALA ZONE-II WSS under Alipurduar Division, PHE Dte. (Part-B) | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000277/2022-2023 | 1663/ALD | 19/09/2022 | 18/03/2023 | MATARA CONSTRUCTION CO | 101.06 | 92.43 | 91.46 | 50
16 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Laying Distribution pipe with DI and UPVC pipe of Baniadabri and Samuktala Bazar Area under SAMUKTALA WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000278/2022-2023 | 1664/ALD | 19/09/2022 | 18/03/2023 | DILIP MAHATO | 100.58 | 92.15 | 91.63 | 46
17 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Laying Distribution pipe with DI and UPVC pipe of Baniadabri and Garokhota Area under SAMUKTALA WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000279/2022-2023 | 1665/ALD | 19/09/2022 | 18/03/2023 | GOUTAM KUMAR DAS | 101.2 | 95.1 | 93.97 | 47
18 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Laying distribution pipeline with UPVC pipe of Samuktala Zone-III Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000280/2022-2023 | 1660/ALD | 19/09/2022 | 18/11/2022 | LONGLAST PIPES (INDIA)PVT.LTD. | 97.26 | 95.08 | 97.76 | 50
19 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Construction of boundary wall (remaining portion) at Headwork site under Samuktala Zone-III PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000289/2023-2024 | 1903/ALD | 07/09/2023 | 01/09/2024 | SWAPAN MALAKAR | 6 | 2.96 | 49.43 | 100
20 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Construction of Pump House at 2nd TW site of Samuktalata PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000293/2022-2023 | 1670/ALD | 19/09/2022 | 18/11/2022 | M/S SADHAN SAHA & CO. | 4.76 | 4.6 | 96.54 | 100
21 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Tube well boring by ODEX-165 Method of drilling, Construction of Pump House, Boundary wall at proposed 6th site of SAMUKTALA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000324/2023-2024 | 2421/ALD | 09/11/2023 | 06/07/2024 | DULAL DAS | 17.57 | 0 | 0 | 0
22 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Cons. Of pathway, surface drain and chatal, Installation of Paver block, land development along with the other allied works at Samuktala Zone-II H/W, 2nd site and 3rd Tube well Site under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000333/2023-2024 | 2519/ALD | 24/11/2023 | 23/01/2024 | CREATIVE UN EMPLOYED ENGINEERSCO OPER SOCYLIMITED | 23.26 | 0 | 0 | 0
23 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Laying of rising main and delivery line connection, construction of boundary wall at headwork site of Samuktala Zone-I PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000340/2023-2024 | 2541/ALD | 28/11/2023 | 26/05/2024 | DIPAK DAS | 28.74 | 3.97 | 13.81 | 100
24 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | 5 nos Tube well boring by ODEX - 165 Method of drilling for the works of augmentation of SAMUKTALA PWSS under Alipurduar Division ,PHE Dte | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000342/2022-2023 | 2221/ALD | 21/11/2022 | 21/12/2022 | S.G. CONSTRUCTION | 32.14 | 25.17 | 78.31 | 50
25 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Laying distribution system with new UPVC pipeline, providing FHTC and other allied works for Samuktala Zone-II PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000355/2022-2023 | 2500/ALD | 13/12/2022 | 12/04/2023 | TAPASH KUMAR BHOWMICK | 88.46 | 80.56 | 91.06 | 50
26 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Laying distribution system with new UPVC pipeline, providing FHTC and other allied works for Samuktala Zone-III PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000356/2022-2023 | 2501/ALD | 13/12/2022 | 12/04/2023 | MADHAB SAHA | 93.21 | 71.72 | 76.94 | 49
27 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Laying distribution system with new UPVC/DI pipeline along with rising and delivery line connection, providing FHTC and others allied works for Samuktala Zone-II PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000393/2022-2023 | 2658/ALD | 22/12/2022 | 17/12/2023 | HARIDAS GHOSH | 88.71 | 79.04 | 89.09 | 48
28 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Laying distribution system with new UPVC/DI pipeline along with rising and delivery line connection, providing FHTC and other allied works for Samuktala Zone-III PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000394/2022-2023 | 2659/ALD | 22/12/2022 | 21/04/2023 | ESCON INDIA | 90.53 | 50.31 | 55.57 | 50
29 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Supply of CIPE Special & CI Jeffy Coupling for Augmentation of Samuktala Water Supply Scheme under Alipurduar Division P.H.E. Dte. (SM/12561) | Alipurduar Sadar Sub Division | Birpara Sub Division,RWS Alipurduar - II Block | ORD/000467/2023-2024 | 673/ALD | 06/03/2024 | 05/04/2024 | BHAGWATI BHUJEL | 11.36 | 5.67 | 49.87 | 15
30 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Land development works at headwork site and laying of new UPVC/DI pipeline for filling gap in distribution system Samuktala Zone-III PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000488/2022-2023 | 3320/ALD | 13/03/2023 | 12/05/2023 | BHAGWATI BHUJEL | 9.19 | 4.58 | 49.82 | 100
31 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Laying of UPVC pipeline for filling of Gap in distribution system Samuktala Zone-I PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000489/2022-2023 | 3321/ALD | 13/03/2023 | 12/05/2023 | CHANDAN KIRTONIA | 5.37 | 5.37 | 100 | 0
32 | ALIPURDUAR |  | Alipurduar Division | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Repairing of HW Site Boundary Wall (15M) Samuktala WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000556/2022-2023 | 3501/ALD | 23/03/2023 | 21/07/2023 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 2.14 | 0.9 | 42.13 | 100
33 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | NEW SEVICE CONNECTION CHARGES FOR SAMUKTALA PWSS ZONE-IIP/H NO.I |  |  | BILL/00741/2023-2024 | BP-2023-24-218 | 13/07/2023 |  | WBSEDCL | 1.54 | 0 | 0 | 0
34 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | NEW SERVICE CONNECTION CHARGE FOR SAMUKTALA ZONE -III P/H NO.I |  |  | BILL/00785/2023-2024 | BP-2023-24-219 | 13/07/2023 |  | WBSEDCL | 1.54 | 0 | 0 | 0
35 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | NEW SERVICE CONNECTION CHARGE FOR SAMUKTALA ZONE -III P/H NO.II |  |  | BILL/00786/2023-2024 | BP-2023-24-220 | 13/07/2023 |  | WBSEDCL | 1.54 | 0 | 0 | 0
36 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | New Service Connection Charge For Samuktala Z-I P/H NO-II |  |  | BILL/00901/2023-2024 | BP-2023-24-221 | 13/07/2023 |  | WBSEDCL | 1.54 | 0 | 0 | 0
37 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | New Service Connection Charge For Samuktala Z-I P/H No.I |  |  | BILL/00902/2023-2024 | BP-2023-24-222 | 13/07/2023 |  | WBSEDCL | 1.54 | 0 | 0 | 0
38 | ALIPURDUAR |  | Northern Mechanical Division II | AUGMENTATION OF SAMUKTALA PIPED WATER SUPPLY SCHEME | SM/12561 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augmentation of SAMUKTALA water supply scheme, TW no I AND II OF ZONE-I , TW no I AND II OF ZONE-II , TW no I AND II OF ZONE-III under Jal Jeevan Mission under NMD-II, PHE Dte.APD. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000002/2023-2024 | 759/NMD-II | 04/04/2023 | 04/05/2023 | AHALYA ENGINEERING WORKS | 63.4 | 54.42 | 85.85 | 40
Total | [13 empty] | 1328.29 | 1039.52 | 78.26