## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | PRODHANPARA PIPED WATER SUPPLY SCHEME | SM/13247 | New | Boring of Tube Well, Construction of Pump House, Boundary Wall, OHR, Laying Of Rising Main, Distribution System including soil test and providing FHTC for Prodhanpara PWSS Under Alipurduar Division, PHE Dte. (2nd call) | Alipurduar RWS | JUNIOR ENGINEER | ORD/000512/2022-2023 | 3394/ALD | 16/03/2023 | 06/09/2024 | MESSRS A.B.G CONSTRUCTION | 425.86 | 84.8 | 19.91 | 20
2 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | PRODHANPARA PIPED WATER SUPPLY SCHEME | SM/13247 | New | Material Requisition To Resource Division |  |  | RTOR000093/2023-2024 | 117/ALD | 10/01/2024 |  | Resource Division | 8.33 | 0 | 0 | 0
3 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | PRODHANPARA PIPED WATER SUPPLY SCHEME | SM/13247 | New | QUOTATION FOR NSC AT PRADHAN PARA PH NO-I |  |  | BILL/01809/2023-2024 | BP-2023-24-374 | 27/09/2023 |  | WBSEDCL | 3.96 | 0 | 0 | 0
4 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | PRODHANPARA PIPED WATER SUPPLY SCHEME | SM/13247 | New | NEW SERVICE CONNECTION CHARGES FOR PRADHAN PARA PWSS P/H NO-II |  |  | BILL/02752/2023-2024 | BP-2023-24-622 | 20/02/2024 |  | WBSEDCL | 7.75 | 0 | 0 | null
5 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | PRODHANPARA PIPED WATER SUPPLY SCHEME | SM/13247 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Pradhan Para water supply scheme, TW no I and II of under Northern Mechanical Division-II, PHE Dte.APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000691/2023-2024 | 2170/NMD-II | 27/07/2023 | 26/08/2023 | SAIKAT SINHA | 18.2 | 6.81 | 37.44 | 50
Total | [13 empty] | 464.11 | 91.61 | 19.74