## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar - II | Alipurduar Division | DAKSHIN MAJIDKHANA PIPED WATER SUPPLY SCHEME. | SM/13305 | New | Supply of DI pipe & CI special for Dakhin Majidkhana PWSS under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000046/2023-2024 | 392/ALD | 19/05/2023 | 18/06/2023 | TAPASH KUMAR BHOWMICK | 40.11 | 21.15 | 52.73 | 80
2 | ALIPURDUAR | Alipurduar - II | Alipurduar Division | DAKSHIN MAJIDKHANA PIPED WATER SUPPLY SCHEME. | SM/13305 | New | Providing balance FHTC for Dakshin Majidkhana PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000210/2023-2024 | 1564/ALD | 23/08/2023 | 07/10/2023 | HARI CONSTRUCTION | 6.77 | 0 | 0 | 0
3 | ALIPURDUAR | Alipurduar - II | Alipurduar Division | DAKSHIN MAJIDKHANA PIPED WATER SUPPLY SCHEME. | SM/13305 | New | Supply of CIDF & CISS Pipes and specials for Dakshin Majidkhana WSS Under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000228/2023-2024 | 1605/ALD | 25/08/2023 | 24/09/2023 | HARI CONSTRUCTION | 6.76 | 0 | 0 | 0
4 | ALIPURDUAR | Alipurduar - II | Alipurduar Division | DAKSHIN MAJIDKHANA PIPED WATER SUPPLY SCHEME. | SM/13305 | New | Laying of rising main/distribution pipeline, supply of DI pipe and specials, horizontal boring by HDD method, bridge and culvert crossing, along with the other allied works at Dakshin Majidkhana PWSS under under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000395/2023-2024 | 206/ALD | 16/01/2024 | 14/07/2024 | HARIDAS GHOSH | 41.16 | 13.61 | 33.07 | 25
5 | ALIPURDUAR | Alipurduar - II | Alipurduar Division | DAKSHIN MAJIDKHANA PIPED WATER SUPPLY SCHEME. | SM/13305 | New | Cons. of pump house and Sinking of 250 mm x 200 mm X 150 mtr. Big dia. TW at HW and 2nd site, LDS with UPVC pipeline, Cons. of 200 cum OHR as per Departmental Design and drawing inclu. Soil testing, providing FHTC and others allied works for Dakshin Majidkhana PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000427/2022-2023 | 2854/ALD | 17/01/2023 | 10/07/2024 | HARIDAS GHOSH | 390.45 | 309.56 | 79.28 | 75
6 | ALIPURDUAR | Alipurduar - II | Alipurduar Division | DAKSHIN MAJIDKHANA PIPED WATER SUPPLY SCHEME. | SM/13305 | New | Material Requisition To Resource Division |  |  | RTOR000034/2023-2024 | 1472/ALD | 16/08/2023 |  | Resource Division | 24.3 | 0 | 0 | 0
7 | ALIPURDUAR | Alipurduar - II | Alipurduar Division | DAKSHIN MAJIDKHANA PIPED WATER SUPPLY SCHEME. | SM/13305 | New | Material Requisition To Resource Division |  |  | RTOR000047/2023-2024 | 2395/ALD | 08/11/2023 |  | Resource Division | 8.64 | 0 | 0 | 0
8 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | DAKSHIN MAJIDKHANA PIPED WATER SUPPLY SCHEME. | SM/13305 | New | NEW SERVICE CONNECTIO CHARGE FOR DAKSHIN MAJIDKHANA W/S/S P/H NO.1 |  |  | BILL/00591/2023-2024 | BP-2023-24-178 | 15/06/2023 |  | WBSEDCL | 1.41 | 0 | 0 | 0
9 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | DAKSHIN MAJIDKHANA PIPED WATER SUPPLY SCHEME. | SM/13305 | New | QUOTATION FOR NEW SERVICE CONNECTION AT DAKSHIN MAJIDKHANA PWSS P/H NO. II |  |  | BILL/01452/2023-2024 | BP-2023-24-292 | 21/08/2023 |  | WBSEDCL | 5.99 | 0 | 0 | 0
10 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | DAKSHIN MAJIDKHANA PIPED WATER SUPPLY SCHEME. | SM/13305 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DAKSHIN MAJIDKHANA water supply scheme, TW no I & II under Northern Mechanical Division-II, PHE Dte. Alipurduar | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000055/2023-2024 | 1165/NMD-II | 15/06/2023 | 15/07/2023 | SUBODH KUMAR BANIK | 21.66 | 10.16 | 46.9 | 100
Total | [13 empty] | 547.25 | 354.48 | 64.78