## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kumargram | Alipurduar Division | JAYANTI TEA GARDEN -II AREA PIPED WATER SUPPLY SCHEME | SM/13448 | New | Cons of PH AND TW Boring by ODEX-165 drilling at HW site and 2nd site , LDS with HDPE P/LINE INCL RM and delivery connection , CONS of 100 Cum OHR along with the Soil investigation works , providing FHTC and others for Jayanti Tea Garden-II PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000132/2023-2024 | 637/ALD | 06/06/2023 | 03/12/2023 | ACHINTA SAHA | 170.77 | 55.02 | 32.22 | 45
2 | ALIPURDUAR | Kumargram | Alipurduar Division | JAYANTI TEA GARDEN -II AREA PIPED WATER SUPPLY SCHEME | SM/13448 | New | Tubewell boring by ODEX-195 method of drilling including rising main connection, repair & renovation of PH, B/wall and Main building of inspection bungalow including painting works, cons of pathway, surface drain, cons of balance civil works of annex building other allied works at Jayanti Inspection bungalow under Alipurduar Divn, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000327/2023-2024 | 2424/ALD | 10/11/2023 | 08/02/2024 | TAPASH KUMAR BHOWMICK | 53.99 | 0 | 0 | 0
3 | ALIPURDUAR | Kumargram | Alipurduar Division | JAYANTI TEA GARDEN -II AREA PIPED WATER SUPPLY SCHEME | SM/13448 | New | Supply of CIDF/CIPE pipes and specials for Jayanti TG-II Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division,Birpara Sub Division | ORD/000464/2023-2024 | 607/ALD | 29/02/2024 | 30/03/2024 | BARMAN ENTERPRISE | 8.6 | 0 | 0 | 61
4 | ALIPURDUAR | Kumargram | Alipurduar Division | JAYANTI TEA GARDEN -II AREA PIPED WATER SUPPLY SCHEME | SM/13448 | New | Material Requisition To Resource Division |  |  | RTOR000108/2023-2024 | 132/ALD | 10/01/2024 |  | Resource Division | 3.47 | 0 | 0 | 0
5 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | JAYANTI TEA GARDEN -II AREA PIPED WATER SUPPLY SCHEME | SM/13448 | New | Qutation for Jayani TG-2 P/HNO-I |  |  | BILL/02165/2023-2024 | BP-2023-24-470 | 12/12/2023 |  | WBSEDCL | 16.18 | 0 | 0 | 0
6 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | JAYANTI TEA GARDEN -II AREA PIPED WATER SUPPLY SCHEME | SM/13448 | New | QUOTATION |  |  | BILL/02210/2023-2024 | BP-2023-24-483 | 12/12/2023 |  | WBSEDCL | 3.05 | 0 | 0 | 0
7 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | JAYANTI TEA GARDEN -II AREA PIPED WATER SUPPLY SCHEME | SM/13448 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Jayanti Area TG II water supply scheme, TW no I and II of under Northern Mechanical Division-II, PHE Dte.APD | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000818/2023-2024 | 2390/NMD-II | 09/08/2023 | 08/09/2023 | SUNLIT | 18.09 | 0 | 0 | 0
Total | [13 empty] | 274.16 | 55.02 | 20.07