## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Madarihat | Alipurduar Division | UTTAR RANGALIBAZNA PIPED WATER SUPPLY SCHEME | SM/14222 | New | Providing FHTC from existing distribution system as per specification for Uttar Rangalibazna PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000304/2023-2024 | 2135/ALD | 03/10/2023 | 02/11/2023 | MANI PRADHAN | 1.08 | 0 | 0 | 0
2 | ALIPURDUAR | Madarihat | Alipurduar Division | UTTAR RANGALIBAZNA PIPED WATER SUPPLY SCHEME | SM/14222 | New | Cons. of Rig bored TW(2nos) by ODEX-165 method of drilling at HW and 2nd site, cons of 100 cum OHR at HW including soil testing, cons. of P/H and B/W at HW,2nd site, Laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing , providing FHTC and others allied works for Uttar Rangalibazna PWSS under Birpara Sub-Division, Alipurduar Division, PHE DTE. | Birpara A.E | Birpara Sub Division | ORD/000546/2022-2023 | 3570/ALD | 27/03/2023 | 23/09/2023 | SAMIRON PODDER | 271.9 | 53.88 | 19.82 | 11
3 | ALIPURDUAR | Madarihat | Alipurduar Division | UTTAR RANGALIBAZNA PIPED WATER SUPPLY SCHEME | SM/14222 | New | Material Requisition To Resource Division |  |  | RTOR000055/2023-2024 | 2701/ALD | 12/12/2023 |  | Resource Division | 84.45 | 0 | 0 | 0
4 | ALIPURDUAR | Madarihat | Alipurduar Division | UTTAR RANGALIBAZNA PIPED WATER SUPPLY SCHEME | SM/14222 | New | Material Requisition To Resource Division |  |  | RTOR000090/2023-2024 | 114/ALD | 10/01/2024 |  | Resource Division | 4.49 | 0 | 0 | 0
5 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | UTTAR RANGALIBAZNA PIPED WATER SUPPLY SCHEME | SM/14222 | New | NEW CONNECTION SETRVICE FOR UTTAR RANGALIBAZNA PWSS P/H NO I APPLICATION NO 4003065172 |  |  | BILL/01793/2023-2024 | BP-2023-24-362 | 27/09/2023 |  | WBSEDCL | 7.7 | 0 | 0 | 0
6 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | UTTAR RANGALIBAZNA PIPED WATER SUPPLY SCHEME | SM/14222 | New | NEW CONNECTION SERVICE FOR UTTAR RANGALIBAZNA PWSS P/H NO II |  |  | BILL/01796/2023-2024 | BP-2023-24-363 | 27/09/2023 |  | WBSEDCL | 5.74 | 0 | 0 | 0
7 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | UTTAR RANGALIBAZNA PIPED WATER SUPPLY SCHEME | SM/14222 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for UTTAR RANGALIBAZNA water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte. Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000685/2023-2024 | 2139/NMD-II | 27/07/2023 | 26/08/2023 | DILIP MAHATO | 18.33 | 0 | 0 | 0
Total | [13 empty] | 393.7 | 53.88 | 13.69