## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong -I | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for Tashiding forest Village under Tashiding GP in Kalimpong Block I in connecion with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte., Kalimpong. | SM/10600 | New | Creating gravity based Provision Of Drinking water from spring water source Tashiding forest village under Tashiding Gram Panchayat under Kalimpong Block-I in the District of Kalimpong Under Neorakhola water Supply Division ,Kalimpong PHE Dte | Assistant Engineer I | Junior Engineer IV | ORD/000065/2022-2023 | 572/NKWSMD | 26/05/2022 | 24/08/2022 | SONAM TSHERING LEPCHA | 10.2 | 0 | 0 | 75
2 | KALIMPONG | Kalimpong -I | Neorakhola W/S & Mtc.Div. | Gravity based piped water supply scheme for Tashiding forest Village under Tashiding GP in Kalimpong Block I in connecion with implementation in the district of Kalimpong under Neorakhola W/S & Mtc, Div. PHE. Dte., Kalimpong. | SM/10600 | New | Material Requisition To Resource Division |  |  | RTOR000100/2022-2023 | 1554/NKWSMD | 19/10/2022 |  | Resource Division | 0.08 | 0 | 0 | 0
Total | [13 empty] | 10.28 | 0 | 0