## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM CHIP CHHIPEY JHORA TO CFC FOREST VILLAGE | SM/10741 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED |  |  | BILL/00456/2023-2024 | BP-2023-24-289 | 01/11/2023 |  | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0 | 0
2 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM CHIP CHHIPEY JHORA TO CFC FOREST VILLAGE | SM/10741 | New | FOREST PAYMENT |  |  | BILL/00962/2023-2024 | BP-2023-24-650 | 28/03/2024 |  | WEST BENGAL PARIVESH CAMPA | 5.55 | 0 | 0 | 0
3 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM CHIP CHHIPEY JHORA TO CFC FOREST VILLAGE | SM/10741 | New | PIPED WATER SUPPLY SCHEME FROM CHIP CHHIPEY JHORA TO CFC FOREST VILLAGE UNDER GORUBATHAN BLOCK KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. |  |  | ORD/000075/2022-2023 | 591/NKWSMD | 26/05/2022 | 25/07/2022 | MAHADEO PRASAD AGARWAL & CO | 82.95 | 17.16 | 20.69 | 85
Total | [13 empty] | 105.23 | 17.16 | 16.31