## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | Mini Piped Water Supply Scheme for Lehti Forest Village under Block Gorubathan District Kalimpong | SM/10820 | New | Implementation of ODEX tube well based 02(two) numbers of pipe water supply scheme having provision of 2(two) numbers of RCC OHR viz 150 cum & 150 cum and other related works for 6(six) villages in GTA area. |  |  | ORD/000095/2022-2023 | 826/NKWSMD | 30/06/2022 | 25/02/2023 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 710.19 | 0 | 0 | 80
2 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | Mini Piped Water Supply Scheme for Lehti Forest Village under Block Gorubathan District Kalimpong | SM/10820 | New | Material Requisition To Resource Division |  |  | RTOR000157/2022-2023 | 2369/NKWSMD | 03/02/2023 |  | Resource Division | 2.13 | 0 | 0 | 0
Total | [13 empty] | 712.33 | 0 | 0