## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source for 03 Numbers of Health Centers in Kalimpong Block -II under the District of Kalimpong ,under Neorakhola water Suppply Division ,Kalimpong PHE Dte. | SM/11369 | Health Center | Creating Gravity based Provision Of Drinking water from spring water source for Upper Dalep Health Center, Pedong G.P in Kalimpong Block -II under the District of Kalimpong, under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate, Kalimpong. |  | Junior Engineer III | ORD/000212/2022-2023 | 985/NKWSMD | 12/07/2022 | 11/08/2022 | YAMA CONSTRUCTIONS LLP | 4.85 | 4.24 | 87.34 | 0
2 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source for 03 Numbers of Health Centers in Kalimpong Block -II under the District of Kalimpong ,under Neorakhola water Suppply Division ,Kalimpong PHE Dte. | SM/11369 | Health Center | Creating gravity based Provision of Drinking water from spring water source for Kashyone Health sub center, Kashyone G.P in Kalimpong Block -II under the District of Kalimpong, under Neorakhola Water Supply & Maintenance Division, P.H.E. Directorate, Kalimpong. |  | Junior Engineer III | ORD/000213/2022-2023 | 986/NKWSMD | 12/07/2022 | 11/08/2022 | YAMA CONSTRUCTIONS LLP | 4.85 | 4.09 | 84.29 | 0
3 | KALIMPONG |  | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source for 03 Numbers of Health Centers in Kalimpong Block -II under the District of Kalimpong ,under Neorakhola water Suppply Division ,Kalimpong PHE Dte. | SM/11369 | Health Center | Creating gravity based Provision Of Drinking water from spring water source Tendrabong health sub Center, Sakyong G.P Kalimpong Block -II under the District of Kalimpong, under Neorakhola Water Supply & Maintenance Division, P.H.E. Directorate, Kalimpong. | Assistant Engineer I |  | ORD/000214/2022-2023 | 987/NKWSMD | 12/07/2022 | 11/08/2022 | YAMA CONSTRUCTIONS LLP | 4.85 | 0.33 | 6.7 | 0
Total | [13 empty] | 14.55 | 8.65 | 59.43