## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong - II | Neorakhola W/S & Mtc.Div. | Mayrong Forest & Tendrabong Village ( Partly) Piped Water Supply Scheme (PWSS) under Sakyong G.P, Block- Kalimpong-II, P.S- Kalimpong, District: Kalimpong. | SM/11806 | New | new connection |  |  | BILL/00009/2023-2024 | BP-2023-24-5 | 25/04/2023 |  | WBSEDCL | 0.44 | 0 | 0 | 0
2 | KALIMPONG | Kalimpong - II | Neorakhola W/S & Mtc.Div. | Mayrong Forest & Tendrabong Village ( Partly) Piped Water Supply Scheme (PWSS) under Sakyong G.P, Block- Kalimpong-II, P.S- Kalimpong, District: Kalimpong. | SM/11806 | New | Piped Water Supply Scheme for Mayrong Forest & Tendrabong Village (Partly) under Sakyong G.P, Block- Kalimpong-II, under Neorakhola Water Supply & Maintenence Division, P.H.Engineering Directorate, District-Kalimpong. | Assistant Engineer I | Junior Engineer III | ORD/000225/2022-2023 | 1155/NKWSMD | 12/08/2022 | 08/02/2023 | JUSTINE BHUTIA | 186.36 | 85.3 | 45.77 | 75
Total | [13 empty] | 186.8 | 85.3 | 45.66