## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PAREN FOREST PIPED WATER SUPPLY SCHEME | SM/13609 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED |  |  | BILL/00456/2023-2024 | BP-2023-24-289 | 01/11/2023 |  | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0 | 0
2 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PAREN FOREST PIPED WATER SUPPLY SCHEME | SM/13609 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED |  |  | BILL/00502/2023-2024 | BP-2023-24-302 | 09/11/2023 |  | WEST BENGAL PARIVESH CAMPA | 5.25 | 0 | 0 | 0
3 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PAREN FOREST PIPED WATER SUPPLY SCHEME | SM/13609 | New | FOREST PAYMENT |  |  | BILL/00962/2023-2024 | BP-2023-24-650 | 28/03/2024 |  | WEST BENGAL PARIVESH CAMPA | 5.55 | 0 | 0 | 0
4 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PAREN FOREST PIPED WATER SUPPLY SCHEME | SM/13609 | New | CREATING GRAVITY BASED PROVISION OF DRINKING WATER FROM SPRING WATER SOURCE FOR PAREN FOREST VILLAGE, DHAULA (PART) UNDER PATEN GODAK GRAM PANCHAYAT UNDER GORUBATHAN BLOCK IN THE DISTRICT OF KALIMPONG UNDER NEORAKHOLA WATER SUPPLY AND MAINTENANCE DIVISION, PUBLIC HEALTH ENGINEERING DIRECTORATE, KALIMPONG (SM/13609) | Assistant Engineer II | Junior Engineer III | ORD/000090/2023-2024 | 711/NKWSMD | 17/07/2023 | 13/01/2024 | SILAN GURUNG | 92.4 | 0 | 0 | 70
5 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PAREN FOREST PIPED WATER SUPPLY SCHEME | SM/13609 | New | Material Requisition To Resource Division |  |  | RTOR000070/2023-2024 | 756/NKWSMD | 19/07/2023 |  | Resource Division | 0.31 | 0 | 0 | 0
Total | [13 empty] | 120.24 | 0 | 0