## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | KUMAI FOREST PIPED WATER SUPPLY SCHEME. | SM/13612 | New | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED |  |  | BILL/00456/2023-2024 | BP-2023-24-289 | 01/11/2023 |  | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0 | 0
2 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | KUMAI FOREST PIPED WATER SUPPLY SCHEME. | SM/13612 | New | FOREST PAYMENT |  |  | BILL/00962/2023-2024 | BP-2023-24-650 | 28/03/2024 |  | WEST BENGAL PARIVESH CAMPA | 5.55 | 0 | 0 | 0
3 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | KUMAI FOREST PIPED WATER SUPPLY SCHEME. | SM/13612 | New | Creating Gravity Based Water Supply Scheme for Kumai Forest Under Gorubathan Block Under Kalimpong District Under P.H.E Dte. | Assistant Engineer I | Junior Engineer III | ORD/000055/2023-2024 | 416/NKWSMD | 05/06/2023 | 31/01/2024 | SACHIN RAI | 279.21 | 0 | 0 | 45
4 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | KUMAI FOREST PIPED WATER SUPPLY SCHEME. | SM/13612 | New | Material Requisition To Resource Division |  |  | RTOR000054/2023-2024 | 450/NKWSMD | 07/06/2023 |  | Resource Division | 1.5 | 0 | 0 | 0
Total | [13 empty] | 302.99 | 0 | 0