## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong - II | Neorakhola W/S & Mtc.Div. | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GIT DUBLING KHASMAHAL (PART) (POCHAK HABITATION) UNDER GITDABLING G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | SM/13617 | New | FOREST PAYMENT |  |  | BILL/00961/2023-2024 | BP-2023-24-645 | 28/03/2024 |  | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0 | 0
2 | KALIMPONG | Kalimpong - II | Neorakhola W/S & Mtc.Div. | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GIT DUBLING KHASMAHAL (PART) (POCHAK HABITATION) UNDER GITDABLING G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | SM/13617 | New | Proposed Pumping Based Piped Water Supply Scheme For Git Dubling Khasmahal (Part) (Pochak Habitation) Under Gitdabling G.P, Block : Kalimpong - II. |  |  | ORD/000272/2022-2023 | 1874/NKWSMD | 14/12/2022 | 11/08/2023 | YAMA CONSTRUCTIONS LLP | 419.84 | 82.25 | 19.59 | 80
3 | KALIMPONG | Kalimpong - II | Neorakhola W/S & Mtc.Div. | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GIT DUBLING KHASMAHAL (PART) (POCHAK HABITATION) UNDER GITDABLING G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | SM/13617 | New | Material Requisition To Resource Division |  |  | RTOR000220/2022-2023 | 2564/NKWSMD | 17/02/2023 |  | Resource Division | 1.48 | 0 | 0 | 0
Total | [13 empty] | 432.91 | 82.25 | 19