## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | TODAY TANGTA KHASMAHAL PWSS | SM/14171 | New | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA |  |  | BILL/00194/2023-2024 | BP-2023-24-155 | 23/08/2023 |  | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0 | 0
2 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | TODAY TANGTA KHASMAHAL PWSS | SM/14171 | New | Proposed Creating gravity based piped water supply scheme for Zone 3 under Today Tangta Khasmahal under Gorubathan Block under Kalimpong District under PHE Dte. | Assistant Engineer I | Junior Engineer IV | ORD/000020/2023-2024 | 102/NKWSMD | 28/04/2023 | 27/04/2024 | MAHADEO PRASAD AGARWAL & CO | 493.17 | 0 | 0 | 60
3 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | TODAY TANGTA KHASMAHAL PWSS | SM/14171 | New | PROPOSED Creating gravity based piped water supply scheme for Zone 1 under Today Tangta Khasmahal under Gorubathan Block under Kalimpong District under PHE Dte | Assistant Engineer II | Junior Engineer III | ORD/000302/2022-2023 | 2353/NKWSMD | 01/02/2023 | 01/02/2024 | TASHI BHUTIA | 364.86 | 0 | 0 | 65
4 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | TODAY TANGTA KHASMAHAL PWSS | SM/14171 | New | PROPOSED Creating gravity based piped water supply scheme for Zone 2 under Today Tangta Khasmahal under Gorubathan Block under Kalimpong District under PHE Dte. | Assistant Engineer I | Junior Engineer IV | ORD/000303/2022-2023 | 2354/NKWSMD | 01/02/2023 | 01/02/2024 | TASHI BHUTIA | 438.07 | 0 | 0 | 0
5 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | TODAY TANGTA KHASMAHAL PWSS | SM/14171 | New | PROPOSED Creating gravity based piped water supply scheme for Zone 4 under Today Tangta Khasmahal under Gorubathan Block under Kalimpong District under PHE Dte | Assistant Engineer II | Junior Engineer III | ORD/000304/2022-2023 | 2361/NKWSMD | 01/02/2023 | 01/02/2024 | MAHADEO PRASAD AGARWAL & CO | 298.82 | 116.35 | 38.94 | 70
6 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | TODAY TANGTA KHASMAHAL PWSS | SM/14171 | New | Material Requisition To Resource Division |  |  | RTOR000022/2023-2024 | 207/NKWSMD | 10/05/2023 |  | Resource Division | 1.08 | 0 | 0 | 0
7 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | TODAY TANGTA KHASMAHAL PWSS | SM/14171 | New | Material Requisition To Resource Division |  |  | RTOR000215/2022-2023 | 2562/NKWSMD | 17/02/2023 |  | Resource Division | 4.9 | 0 | 0 | 0
Total | [13 empty] | 1609.3 | 116.35 | 7.23