## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong - II | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LAVA FOREST (PART) UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | SM/15042 | New | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LAVA FOREST (PART) UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | Assistant Engineer I | Junior Engineer IV | ORD/000309/2022-2023 | 2489/NKWSMD | 09/02/2023 | 07/10/2023 | THUPDEN BHUTIA | 194.1 | 0 | 0 | 50
2 | KALIMPONG | Kalimpong - II | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LAVA FOREST (PART) UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | SM/15042 | New | Material Requisition To Resource Division |  |  | RTOR000201/2022-2023 | 2550/NKWSMD | 17/02/2023 |  | Resource Division | 0.99 | 0 | 0 | 0
3 | KALIMPONG | Kalimpong - II | Neorakhola W/S & Mtc.Div. | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LAVA FOREST (PART) UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | SM/15042 | New | Material Requisition To Resource Division |  |  | RTOR000235/2022-2023 | 2724/NKWSMD | 03/03/2023 |  | Resource Division | 0.99 | 0 | 0 | 0
Total | [13 empty] | 196.09 | 0 | 0