## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | KUMAI FOREST (PART) & KUMAI TEA GARDEN PWSS | SM/15554 | New | KUMAI FOREST(PART) & KUMAI TEA GARDEN (PART) PIPED WATER SUPPLY SCHEME SPRING WATER SUPPLY SCHEME (TSM/016058) |  |  | ORD/000335/2022-2023 | 2731/NKWSMD | 03/03/2023 | 30/08/2023 | PUSHPA KUMAR RIZAL | 195.31 | 0 | 0 | 50
2 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | KUMAI FOREST (PART) & KUMAI TEA GARDEN PWSS | SM/15554 | New | Material Requisition To Resource Division |  |  | RTOR000251/2022-2023 | 2749/NKWSMD | 06/03/2023 |  | Resource Division | 0.86 | 0 | 0 | 0
Total | [13 empty] | 196.17 | 0 | 0