## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong -I | Neorakhola W/S & Mtc.Div. | KALIMPONG KHASMAHAL (PART) PIPED WATER SUPPLY SCHEME UNDER TASHIDING G.P, BLOCK-KALIMPONG-I, DISTRICT:-KALIMPONG | SM/16230 | New | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR KALIMPONG KHASMAHAL PIPED WATER SUPPLY SCHEME, UNDER TASHIDING G.P BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG. |  |  | ORD/000067/2023-2024 | 363/NKWSMD | 29/05/2023 | 28/05/2024 | YAMA CONSTRUCTIONS LLP | 896.8 | 125 | 13.94 | 80
2 | KALIMPONG | Kalimpong -I | Neorakhola W/S & Mtc.Div. | KALIMPONG KHASMAHAL (PART) PIPED WATER SUPPLY SCHEME UNDER TASHIDING G.P, BLOCK-KALIMPONG-I, DISTRICT:-KALIMPONG | SM/16230 | New | Material Requisition To Resource Division |  |  | RTOR000060/2023-2024 | 533/NKWSMD | 13/06/2023 |  | Resource Division | 6.58 | 0 | 0 | 0
Total | [13 empty] | 903.38 | 125 | 13.84