## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM CHAR CHAREY JHORA TO PUBUNG BUSTY | SM/09543 | New | P.W.S SCHEME FROM CHAR CHAREY JHORA TO PUBUNG BUSTY AND ITS ADJOINING AREAS IN POKRAIBONG G.P GORUBATHAN BLOCK, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME, DISTRICT- KALIMPONG. |  |  | ORD/000104/2021-2022 | 628/NKWSMD | 21/02/2022 | 17/01/2023 | SRINIWAS AGARWAL | 353.99 | 109.22 | 30.85 | 80
2 | KALIMPONG | Gorubathan | Neorakhola W/S & Mtc.Div. | PWS SCHEME FROM CHAR CHAREY JHORA TO PUBUNG BUSTY | SM/09543 | New | Material Requisition To Resource Division |  |  | RTOR000036/2021-2022 | 840/NKWSMD | 21/03/2022 |  | Resource Division | 1.17 | 0 | 0 | 0
Total | [13 empty] | 355.16 | 109.22 | 30.75