## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | KALIMPONG | Kalimpong - II | Neorakhola W/S & Mtc.Div. | PWS from Samphong Khola to Kagey Busty District Kalimpong | SM/09548 | New | P.W.S SCHEME FROM SAMPHONG KHOLA TO KAGEY BUSTY UNDER KAGEY G.P. BLOCK-II, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME, DISTRICT- KALIMPONG. |  |  | ORD/000107/2021-2022 | 626/NKWSMD | 21/02/2022 | 21/07/2022 | GARGO TRADERS | 475.53 | 393.64 | 82.78 | 85
2 | KALIMPONG | Kalimpong - II | Neorakhola W/S & Mtc.Div. | PWS from Samphong Khola to Kagey Busty District Kalimpong | SM/09548 | New | SUPPLEMENARY ESTIMATE OF PWS SCHEME FOR SAMPHONG KHOLA TO KAGEY BUSTY UNDER KAGEY G.P., BLOCK-II, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME, DISTRICT-KALIMPONG. |  |  | ORD/000262/2022-2023 | 1654/NKWSMD | 04/11/2022 | 02/02/2023 | ALLIED INSTRUMENTS | 196.63 | 0 | 0 | 50
3 | KALIMPONG | Kalimpong - II | Neorakhola W/S & Mtc.Div. | PWS from Samphong Khola to Kagey Busty District Kalimpong | SM/09548 | New | Material Requisition To Resource Division |  |  | RTOR000034/2021-2022 | 837/NKWSMD | 21/03/2022 |  | Resource Division | 3.54 | 0 | 0 | 0
Total | [13 empty] | 675.69 | 393.64 | 58.26