## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Ramgarh (Zone-I/II) Piped Water Supply Scheme. | SM/06827 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Ramgarh (Zone-I & II) PWSS of Binpur-I Block under Jhargram Division, PHE Dte. |  |  | ORD/000200/2020-2021 | 1403/MD | 26/11/2020 | 25/05/2021 | ASIS KUMAR SARANGI | 76.93 | 62.98 | 81.87 | 1
2 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Ramgarh (Zone-I/II) Piped Water Supply Scheme. | SM/06827 | Retrofitting | Bill for FHTC data entry in IMIS in the District of Paschim Medinipur and Jhargram under Midnaproe Division, PHE Dte. |  |  | VCH/000271/2021-2022 | 8443117 | 31/05/2021 |  | NABOGOPAL ADHIKARI | 0.06 | 0 | 0 | 0
3 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Ramgarh (Zone-I/II) Piped Water Supply Scheme. | SM/06827 | Retrofitting | Bill for FHTC data entry in IMIS in the District of Paschim Medinipur and Jhargram under Midnaproe Division, PHE Dte. |  |  | VCH/000272/2021-2022 | 8443117 | 31/05/2021 |  | RINTU SAMANTA | 0.11 | 0 | 0 | 0
4 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Ramgarh (Zone-I/II) Piped Water Supply Scheme. | SM/06827 | Retrofitting | Bill for FHTC data entry in IMIS in the District of Paschim Medinipur and Jhargram under Midnaproe Division, PHE Dte. |  |  | VCH/000273/2021-2022 | 8443117 | 31/05/2021 |  | PARTHA PRATIM PAL | 0.06 | 0 | 0 | 0
5 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Ramgarh (Zone-I/II) Piped Water Supply Scheme. | SM/06827 | Retrofitting | Bill for FHTC data entry in IMIS in the District of Paschim Medinipur and Jhargram under Midnaproe Division, PHE Dte. |  |  | VCH/000274/2021-2022 | 8443117 | 31/05/2021 |  | SANDIP MANNA | 0.04 | 0 | 0 | 0
6 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Ramgarh (Zone-I/II) Piped Water Supply Scheme. | SM/06827 | Retrofitting | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN RAMGARH (ZONE-I/II)PWSS |  |  | VCH/000614/2021-2022 | 844311 | 02/08/2021 |  | ASIS KUMAR SARANGI | 1.79 | 0 | 0 | 0
7 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Ramgarh (Zone-I/II) Piped Water Supply Scheme. | SM/06827 | Retrofitting | DATA ENTRY FOR FHTC |  |  | VCH/000847/2021-2022 | 8443209 | 27/09/2021 |  | ANIRBAN CHAKRABORTY | 0.12 | 0 | 0 | 0
8 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Ramgarh (Zone-I/II) Piped Water Supply Scheme. | SM/06827 | Retrofitting | DATA ENTRY FOR FHTC |  |  | VCH/000848/2021-2022 | 8443209 | 27/09/2021 |  | GANESH CH NANDY | 0.22 | 0 | 0 | 0
9 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Ramgarh (Zone-I/II) Piped Water Supply Scheme. | SM/06827 | Retrofitting | DATA ENTRY FOR FHTC |  |  | VCH/000849/2021-2022 | 8443209 | 27/09/2021 |  | SOVANDEB MANNA | 0.03 | 0 | 0 | 0
10 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Ramgarh (Zone-I/II) Piped Water Supply Scheme. | SM/06827 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. |  |  | VCH/001401/2020-2021 | 8443457 | 26/03/2021 |  | SOVANDEB MANNA | 0.17 | 0 | 0 | 0
11 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Ramgarh (Zone-I/II) Piped Water Supply Scheme. | SM/06827 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. |  |  | VCH/001402/2020-2021 | 8443357 | 26/03/2021 |  | NABOGOPAL ADHIKARI | 0.12 | 0 | 0 | 0
12 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Ramgarh (Zone-I/II) Piped Water Supply Scheme. | SM/06827 | Retrofitting | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. |  |  | VCH/001403/2020-2021 | 8443457 | 26/03/2021 |  | SIDDHESWAR BAG | 0.2 | 0 | 0 | 0
13 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Ramgarh (Zone-I/II) Piped Water Supply Scheme. | SM/06827 | Retrofitting | FHTC imis data entry. |  |  | VCH/001644/2021-2022 | 8443206 | 26/03/2022 |  | ANIRBAN CHAKRABORTY | 0.15 | 0 | 0 | 0
14 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Ramgarh (Zone-I/II) Piped Water Supply Scheme. | SM/06827 | Retrofitting | FHTC imis data entry. |  |  | VCH/001645/2021-2022 | 8443206 | 26/03/2022 |  | SHRABONTI BERA | 0.14 | 0 | 0 | 0
Total | [13 empty] | 80.12 | 62.98 | 78.6