## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 1 No. P.W.S.S. within Gopiballavpur - I & 2 Nos. P.W.S.S. within Gopiballavpur-II | SM/06831 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Naupara PWSS of Gopiballavpur-II Block under Jhargram Division, PHE Dte. |  |  | ORD/000184/2020-2021 | 1412/MD | 26/11/2020 | 25/05/2021 | ASIS KUMAR SARANGI | 36.77 | 27.31 | 74.25 | 80
2 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 1 No. P.W.S.S. within Gopiballavpur - I & 2 Nos. P.W.S.S. within Gopiballavpur-II | SM/06831 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Alampur PWSS of Gopiballavpur-I Block under Jhargram Division, PHE Dte. |  |  | ORD/000201/2020-2021 | 1398/MD | 26/11/2020 | 25/05/2021 | ASHIM KUMAR DEY | 50.2 | 50.18 | 99.95 | 0
3 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 1 No. P.W.S.S. within Gopiballavpur - I & 2 Nos. P.W.S.S. within Gopiballavpur-II | SM/06831 | Retrofitting | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN 1NO.PWSS WITHIN GOPIBALLAVPUR-1&2 NOS PWSS WITHIN GOPIBALLAVPUR-II |  |  | VCH/000612/2021-2022 | 844310 | 02/08/2021 |  | ASIS KUMAR SARANGI | 0.82 | 0 | 0 | 0
4 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in 1 No. P.W.S.S. within Gopiballavpur - I & 2 Nos. P.W.S.S. within Gopiballavpur-II | SM/06831 | Retrofitting | Extension of Distribution pipe line for left out Habitation in Phul Baria Mouza (0264) in connection with FHTC under Alampur W/S Scheme within Gopiballavpur-I Block Under Jhargram Division, PHE Dte. |  |  | VCH/001201/2021-2022 | 844350 | 09/12/2021 |  | ASIM KUMAR DEY. | 2.67 | 0 | 0 | 0
Total | [13 empty] | 90.46 | 77.49 | 85.66