## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Midnapore Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Khamar Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09382 | Augmentation | Extension of distribution pipe line and FHTC work for Augmentation of Ground Based Khamar PWSS to accommodate FHTC in Binpur-II block within Jhargram district under Jhargram Division, PHE Dte. |  |  | ORD/000015/2022-2023 | 612/MD | 04/04/2022 | 25/04/2022 | M/S. SANKAR KUMAR NAG | 10.11 | 0 | 0 | 0
2 | JHARGRAM |  | Midnapore Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Khamar Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09382 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Khamar PWSS in Binpur-II Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  |  | VCH/001379/2021-2022 | BP-2021-22-406 | 23/02/2022 |  | M/S R. DUTTA & CO | 1.34 | 0 | 0 | 0
3 | JHARGRAM |  | Jhargram Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Khamar Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09382 | Augmentation | Balance Work of Augmentation of Khamar Piped Water Supply Scheme in Binpur-II Block within Jhargram Division under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000094/2023-2024 | 648/JSD | 13/07/2023 | 12/08/2023 | SAUBHIK KUMAR NAG | 4.84 | 4.84 | 100 | 100
4 | JHARGRAM |  | Jhargram Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Khamar Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09382 | Augmentation | SWITCH ROOM SIZE (3.6 MTRX3.00 MTR) WITHOUT SANITATION AT KHAMAR W/S SCHEME UNDER BINPUR-II BLOCK WITHIN JHARGRAM DIVISION, P.H.E. DTE. | Assistant Engineer | Junior Engineer-II | ORD/000143/2023-2024 | 737/JSD | 16/08/2023 | 15/09/2023 | ANJAN KUMAR MAHATA | 2.91 | 0 | 0 | 100
5 | JHARGRAM |  | Jhargram Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Khamar Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09382 | Augmentation | Extension of distribution pipe line and FHTC work for Augmentation of Ground Based Khamar PWSS to accommodate FHTC in Binpur-II block within Jhargram district under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000160/2022-2023 | 612/MD | 04/04/2022 | 25/04/2022 | M/S. SANKAR KUMAR NAG | 10.11 | 9.91 | 98.03 | 1
6 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Khamar Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09382 | Augmentation | New service connection charges |  |  | BILL/00265/2022-2023 | 17/JMD/PFMS/MAR | 06/03/2023 |  | WBSEDCL | 0.21 | 0 | 0 | 0
7 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Khamar Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09382 | Augmentation | Supply, delivery, installation, commissioning of Electro Mechanical accessories for newly constructed Pump house for newly sunk Rig bore T/W at Khamar piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Driller-In-Charge | JE (M),Junior Engineer | ORD/000195/2023-2024 | 2110/JMD | 03/08/2023 | 02/10/2023 | DEBJYOTI BASU | 4.46 | 2.23 | 49.84 | 100
8 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Khamar Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09382 | Augmentation | Supply, delivery, installation, commissioning of submersible pumping machinery and other Electro Mechanical accessories for two (02) nos. newly sunk Rig bore Tube well at Khamar piped water supply scheme at Binpur -II block of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M) | ORD/000673/2022-2023 | 4212/JMD | 28/12/2022 | 27/01/2023 | AMIT DAS | 7.38 | 6.57 | 89.06 | 0
9 | JHARGRAM |  | Jhargram Mechanical Division | Retrofitting to Accommodate FHTC incl. Augmentation of Source under JJM in Ground water based Khamar Water Supply Scheme at Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/09382 | Augmentation | Sinking of (200 mmX 165 mm) RBTW by DTH Method at Khamar PWSS, tube well no.-1 of Binpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000890/2021-2022 | 593/JMD | 23/12/2021 | 27/12/2021 | SUJOY RANJAN BHOWMICK | 0.62 | 0 | 0 | 0
Total | [13 empty] | 41.97 | 23.54 | 56.08