## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Balibandh PWSS (Phase - II) under Jamboni Block. | SM/09385 | Retrofitting | Retrofitting of Ground Water Based W/S Scheme for Baliband PWSS to accommodate FHTC in Block Jamboni under Jhargram Division P.H.E. Dte. (Phase-II) |  |  | ORD/000691/2021-2022 | 288/MD | 15/02/2022 | 01/04/2022 | NRIPENDRA NATH SINGHA | 6.24 | 6.11 | 97.84 | 1
2 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Balibandh PWSS (Phase - II) under Jamboni Block. | SM/09385 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000022/2021-2022 | 2166/MD | 17/12/2021 |  | Resource Division | 0.32 | 0 | 0 | 0
Total | [13 empty] | 6.56 | 6.11 | 93.09