## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Division | Water Supply System at Anganwadi Centers(176 nos.) within Jhargram Block under Jhargram District. | SM/10354 | Anganwadi | Water Supply Arrangement for 176 Nos. Anganwadi Centers At Jhargram Block in Jhargram District under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter |  | ORD/000075/2022-2023 | 382/JHD | 21/10/2022 | 19/01/2023 | M/S. D.K.H.CONSTRUCTION | 293.08 | 182.05 | 62.12 | 70
Total | [13 empty] | 293.08 | 182.05 | 62.12