## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Midnapore Division | Retrofitting to accommodate FHTC under JJM in Pathardahara PWSS (Phase-II) in Nayagram Block under Jhargram district. | SM/10439 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Pathardahara PWSS (Phase-II) Block - Nayagram in the District of Jhargram |  |  | ORD/000035/2022-2023 | 201/JSD | 04/04/2022 | 25/04/2022 | DHUMKETU ENGINEERING PRIVATE LIMITED | 4.05 | 1.6 | 39.45 | 0
2 | JHARGRAM |  | Jhargram Division | Retrofitting to accommodate FHTC under JJM in Pathardahara PWSS (Phase-II) in Nayagram Block under Jhargram district. | SM/10439 | Retrofitting | Retrofitting to accommodate FHTC under JJM in Pathardahara PWSS (Phase-II) Block - Nayagram in the District of Jhargram |  | Junior Engineer-III | ORD/000095/2022-2023 | 201/JSD | 04/04/2022 | 25/04/2022 | DHUMKETU ENGINEERING PRIVATE LIMITED | 4.05 | 2.2 | 54.4 | 100
Total | [13 empty] | 8.1 | 3.8 | 46.92