## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Division | Rejuvenation of Ground Water Based Ramgarh ( Zone-I & II) PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/10485 | Augmentation | Health Assessment (Conducting Non Destructive Test) of Existing RCC O.H.R (Zone-I) of capacity 50000 gallon with staging height of 20 mtr. of Ramgarh Piped Water Supply Scheme at Binpur-I Block under Jhargram Sub Division within Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000021/2022-2023 | 426/JSD | 05/08/2022 | 20/08/2022 | SIRCON ENGINEERING SERVICES | 4.4 | 4.37 | 99.38 | 1
2 | JHARGRAM |  | Jhargram Division | Rejuvenation of Ground Water Based Ramgarh ( Zone-I & II) PWSS to Accommodate FHTC in Binpur-I Block within Jhargram District under Jhargram Division, PHE Dte. | SM/10485 | Augmentation | Replacement of distribution pipe line from Dasbundh to Sarasbedia pond for Ramgarh water supply Scheme (Zone-I). | Assistant Engineer | Junior Engineer-III | ORD/000349/2023-2024 | 971/JSD | 10/11/2023 | 01/12/2023 | KALI GANGA ENTERPRISE | 4.81 | 0 | 0 | 80
Total | [13 empty] | 9.21 | 4.37 | 47.47