## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Dahijuri PWSS to Accommodate FHTC in Binpur-I Block, Jhargram District | SM/10492 | Augmentation | Restoration work for laying of pipeline along Dahijuri Binpur Silda Hatiari Road & Dahijuri-Lalgarh Road due to distribution pipeline of ground wter based Dahijuri PWSS under Jhargram Division ,PHE Dte |  |  | BILL/00028/2023-2024 | BP-2023-24-35 | 15/05/2023 |  | EXECUTIVE ENGINEER, PWD (ROADS) JHARGRAM | 8.6 | 0 | 0 | 0
2 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Dahijuri PWSS to Accommodate FHTC in Binpur-I Block, Jhargram District | SM/10492 | Augmentation | Restoration work for laing pipeline along with Augmentation of Ground Water Based Water Supply Scheme for Dahijuri PWSS to Accommodate FHTC in Binpur-I Block, Jhargram District |  |  | BILL/00767/2023-2024 | BP-2023-24-389 | 10/01/2024 |  | EXECUTIVE ENGINEER, PWD (ROADS) JHARGRAM | 8.6 | 0 | 0 | 0
3 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Dahijuri PWSS to Accommodate FHTC in Binpur-I Block, Jhargram District | SM/10492 | Augmentation | Reconstruction of existing Boundary wall at Head work cum O.H.R. site of Dahijuri W/S Scheme under Rejuvenation of Dahijuri Water Supply scheme within Binpur-I Block and district Jhargram District Midnapore Division, PHE Dte. | Assistant Engineer | Junior Engineer-III | ORD/000002/2019-2020 | 1620/MD | 04/12/2019 | 02/02/2020 | ASHIM KUMAR DEY | 4.72 | 0 | 0 | 100
4 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Dahijuri PWSS to Accommodate FHTC in Binpur-I Block, Jhargram District | SM/10492 | Augmentation | Laying of Distribution pipe line and FHTC work for Augmentation of Ground water based Water Supply for Dahijuri to accommodate FHTC under Binpur-I Block within Jhargram District under Jhargram Division, PHE De. | Assistant Engineer | Junior Engineer-III | ORD/000102/2022-2023 | 619/JHD | 25/11/2022 | 25/12/2022 | UTTAM KUMAR DAS | 128.45 | 63.75 | 49.63 | 70
5 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Dahijuri PWSS to Accommodate FHTC in Binpur-I Block, Jhargram District | SM/10492 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Dohijuri PWSS in Binpur-I Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  | Junior Engineer-III | ORD/000131/2021-2022 | 78/JSD | 25/06/2021 | 09/07/2021 | INDRANIL DUTTA & ASSOCIATES | 3.31 | 3.31 | 100 | 1
6 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Water Supply Scheme for Dahijuri PWSS to Accommodate FHTC in Binpur-I Block, Jhargram District | SM/10492 | Augmentation | Laying of additional distribution pipe line for augmentation of ground water based Dahijuri PWSS to accommodate FHTC in Binpur-I Block within Jhargram district under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-III | ORD/000173/2023-2024 | 744/JSD | 17/08/2023 | 01/10/2023 | JMC, PRO. CHIRANJIT NANDI | 2.36 | 1.18 | 49.98 | 100
7 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Dahijuri PWSS to Accommodate FHTC in Binpur-I Block, Jhargram District | SM/10492 | Augmentation | Supply, delivery & installation of various electro-mechanical accessories for repairing & rejuvenation of pump house no.-II of Dahijuri w/s scheme in the dist. of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/001371/2023-2024 | 2988/JMD | 13/03/2024 | 12/04/2024 | SUJOY RANJAN BHOWMICK | 9.57 | 3.04 | 31.73 | 50
8 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Water Supply Scheme for Dahijuri PWSS to Accommodate FHTC in Binpur-I Block, Jhargram District | SM/10492 | Augmentation | Supply, delivery and installation of Vinyl Sign board for depicting the scheme details of Dahijuri and adjacent water supply schemes for ongoing Solarisation works for the purpose of Geotagging under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001379/2023-2024 | 3061/JMD | 14/03/2024 | 29/03/2024 | MUKHERJEE ART CENTRE | 9.68 | 4.83 | 49.88 | 100
Total | [13 empty] | 175.29 | 76.11 | 43.42