## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jhargram | Jhargram Division | PANCHAMI AND ADJOINING MOJAS PWSS at Jhargram Block. | SM/12325 | New | Sinking of Tube Well , Laying distribution pipe line, Accommodate FHTC (400 nos) under JJM with allied work for PANCHAMI AND ITS ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour and materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000009/2023-2024 | 646/JHD | 11/05/2023 | 09/08/2023 | SUNIL DULE | 79.43 | 56.65 | 71.32 | 80
2 | JHARGRAM | Jhargram | Jhargram Division | PANCHAMI AND ADJOINING MOJAS PWSS at Jhargram Block. | SM/12325 | New | Construction of 150 cum OHR, Laying distribution pipe line, soil investigation for PANCHAMI AND ITS ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour and materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 5th Call (Ref: 1st Call eNIT_16 of 2022-23, SL No.-1 and 2nd Call eNIT_37 of 2023-24, SL No.-1, 3rd Call eNIT_13 of 2023-24, SL No.-1, 4th Call eNIT_22 of 2023-24, SL No.-2) | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000016/2024-2025 | 987/JHD | 16/07/2024 | 11/02/2025 | SRIKANTA MONDAL | 79.97 | 0 | 0 | 0
3 | JHARGRAM | Jhargram | Jhargram Division | PANCHAMI AND ADJOINING MOJAS PWSS at Jhargram Block. | SM/12325 | New | Laying distribution pipe line, Accommodate FHTC (200 nos) for PANCHAMI AND ITS ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour and materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. (2nd Call) | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000037/2023-2024 | 883/JHD | 08/06/2023 | 06/09/2023 | PALCON | 51.64 | 25.46 | 49.3 | 55
4 | JHARGRAM | Jhargram | Jhargram Division | PANCHAMI AND ADJOINING MOJAS PWSS at Jhargram Block. | SM/12325 | New | Pump House , Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board, Accommodate FHTC (336 nos) under JJM with allied work for PANCHAMI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000142/2023-2024 | 1325/JHD | 10/08/2023 | 08/11/2023 | DIVINE | 71.48 | 21.85 | 30.57 | 80
5 | JHARGRAM | Jhargram | Jhargram Division | PANCHAMI AND ADJOINING MOJAS PWSS at Jhargram Block. | SM/12325 | New | Material Requisition To Resource Division |  |  | RTOR000004/2022-2023 | 1592/JHD | 08/09/2023 |  | Resource Division | 33.72 | 0 | 0 | 0
6 | JHARGRAM | Jhargram | Jhargram Mechanical Division | PANCHAMI AND ADJOINING MOJAS PWSS at Jhargram Block. | SM/12325 | New | Additional service connection charges of Panchami-1 water supply scheme |  |  | BILL/00026/2024-2025 | 25/JMD | 24/04/2024 |  | WBSEDCL | 4.12 | 0 | 0 | null
7 | JHARGRAM | Jhargram | Jhargram Mechanical Division | PANCHAMI AND ADJOINING MOJAS PWSS at Jhargram Block. | SM/12325 | New | New service connection |  |  | BILL/00388/2023-2024 | 26/Aug | 29/08/2023 |  | WBSEDCL | 11.35 | 0 | 0 | 0
8 | JHARGRAM | Jhargram | Jhargram Mechanical Division | PANCHAMI AND ADJOINING MOJAS PWSS at Jhargram Block. | SM/12325 | New | New service connection |  |  | BILL/00390/2023-2024 | 28/AUG | 29/08/2023 |  | WBSEDCL | 2.83 | 0 | 0 | 0
9 | JHARGRAM | Jhargram | Jhargram Mechanical Division | PANCHAMI AND ADJOINING MOJAS PWSS at Jhargram Block. | SM/12325 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Panchami & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M) | ORD/000031/2023-2024 | 1229/JMD | 26/05/2023 | 22/11/2023 | JAGANNATH ENTERPRISE | 20.76 | 8.56 | 41.22 | 70
Total | [13 empty] | 355.31 | 112.52 | 31.67