## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Gopiballavpur - II | Central Drilling | TENTULIA AND ADJOINING MOUJAS PWSS | SM/12341 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2 | JHARGRAM | Gopiballavpur - II | Jhargram Division | TENTULIA AND ADJOINING MOUJAS PWSS | SM/12341 | New | Construction of Boundary wall & allied works at 2nd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Tentulia and its Adjoining Mouzas PWSS , Block: - Gopiballavpur-II, District: - Jhargram {TYPE - B} (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer | Junior Engineer-III | ORD/000083/2024-2025 | 784/JSD | 09/08/2024 | 08/09/2024 | GOPESH DEY | 4.76 | 0 | 0 | 0
3 | JHARGRAM | Gopiballavpur - II | Jhargram Division | TENTULIA AND ADJOINING MOUJAS PWSS | SM/12341 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer,Assistant Engineer Headquarter | Junior Engineer, Gopiballavpur Sub Division,Junior Engineer-II | ORD/000298/2023-2024 | 1727/JHD | 30/09/2023 | 26/07/2024 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 0 | 0 | 25
4 | JHARGRAM | Gopiballavpur - II | Jhargram Mechanical Division | TENTULIA AND ADJOINING MOUJAS PWSS | SM/12341 | New | Quotation for new service connection at Tentulia tw-II water supply scheme. |  |  | BILL/00346/2024-2025 | 149/JMD | 31/05/2024 |  | WBSEDCL | 4.3 | 0 | 0 | null
5 | JHARGRAM | Gopiballavpur - II | Jhargram Mechanical Division | TENTULIA AND ADJOINING MOUJAS PWSS | SM/12341 | New | Quotation for new service connection at Tentulia T/W -I water supply scheme. |  |  | BILL/00347/2024-2025 | 150/JMD | 31/05/2024 |  | WBSEDCL | 3.04 | 0 | 0 | null
6 | JHARGRAM | Gopiballavpur - II | Jhargram Mechanical Division | TENTULIA AND ADJOINING MOUJAS PWSS | SM/12341 | New | New Service connection |  |  | BILL/00407/2023-2024 | 2/JMD | 07/09/2023 |  | WBSEDCL | 3.1 | 0 | 0 | 0
7 | JHARGRAM | Gopiballavpur - II | Jhargram Mechanical Division | TENTULIA AND ADJOINING MOUJAS PWSS | SM/12341 | New | New Service connection |  |  | BILL/00408/2023-2024 | 3/JMD | 07/09/2023 |  | WBSEDCL | 4.75 | 0 | 0 | 0
Total | [13 empty] | 33644.48 | 0 | 0