## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur - I | Central Drilling | SIMLADANGA AND ADJOINING MOUJAS PWSS | SM/12343 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2 | JHARGRAM | Binpur - I | Jhargram Division | SIMLADANGA AND ADJOINING MOUJAS PWSS | SM/12343 | New | Construction of Boundary wall allied works at 3rd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Simladanga and its Adjoining Mouzas PWSS , Block Binpur-I, District Jhargram TYPE - B Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L | Assistant Engineer | Junior Engineer, Jhargram Sub-Division | ORD/000059/2024-2025 | 778/JSD | 09/08/2024 | 08/09/2024 | ARUP KUMAR MAITI | 4.39 | 0 | 0 | 0
3 | JHARGRAM | Binpur - I | Jhargram Division | SIMLADANGA AND ADJOINING MOUJAS PWSS | SM/12343 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House & Providing Functional Household Tap Connection (24693) including 02(Two) Years Operation & Maintenance For 14 Nos Pipe water supply Scheme within BINPUR-I Block Under Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer | Junior Engineer Binpur-I block | ORD/000069/2023-2024 | 1113/JHD | 18/07/2023 | 24/03/2024 | M/S SWACH ENVIRONMENT PRIVATE LTD. | 7215.68 | 1.53 | 0.02 | 40
4 | JHARGRAM | Binpur - I | Jhargram Division | SIMLADANGA AND ADJOINING MOUJAS PWSS | SM/12343 | New | Construction of Boundary wall & allied works at 2nd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Simladanga and its Adjoining Mouzas PWSS , Block: - Binpur-I, District: - Jhargram {TYPE - B} (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer | Junior Engineer, Jhargram Sub-Division | ORD/000079/2024-2025 | 776/JSD | 09/08/2024 | 08/09/2024 | CONSTRUCTURE | 4.81 | 0 | 0 | 0
5 | JHARGRAM | Binpur - I | Jhargram Division | SIMLADANGA AND ADJOINING MOUJAS PWSS | SM/12343 | New | Material Requisition To Resource Division |  |  | RTOR000042/2023-2024 | 1553/JHD | 07/09/2023 |  | Resource Division | 181.8 | 0 | 0 | 0
6 | JHARGRAM | Binpur - I | Jhargram Mechanical Division | SIMLADANGA AND ADJOINING MOUJAS PWSS | SM/12343 | New | Quotation for new service connection at Simladanga tw-III water supply scheme. |  |  | BILL/00389/2024-2025 | 185/JMD | 11/06/2024 |  | WBSEDCL | 5.94 | 0 | 0 | null
Total | [13 empty] | 28752.39 | 1.53 | 0.01