## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Gopiballavpur - II | Central Drilling | KENDANA AND ADJOINING MOUJAS PWSS | SM/12346 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2 | JHARGRAM | Gopiballavpur - II | Jhargram Division | KENDANA AND ADJOINING MOUJAS PWSS | SM/12346 | New | Construction of Boundary wall allied works at 2nd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Kendana and its Adjoining Mouzas PWSS , Block Gopiballavpur-II, District Jhargram TYPE - B Total length 50 mtr,column size 250250mm,3.00 M cc ht.- 2.300mtr from G.L | Assistant Engineer | Junior Engineer, Jhargram Sub-Division,Junior Engineer-III | ORD/000060/2024-2025 | 781/JSD | 09/08/2024 | 08/09/2024 | DEBABRATA DUTTA | 4.71 | 0 | 0 | 0
3 | JHARGRAM | Gopiballavpur - II | Jhargram Division | KENDANA AND ADJOINING MOUJAS PWSS | SM/12346 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer,Assistant Engineer Headquarter | Junior Engineer, Gopiballavpur Sub Division,Junior Engineer-II | ORD/000298/2023-2024 | 1727/JHD | 30/09/2023 | 26/07/2024 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 0 | 0 | 25
4 | JHARGRAM | Gopiballavpur - II | Jhargram Mechanical Division | KENDANA AND ADJOINING MOUJAS PWSS | SM/12346 | New | Quotation for new service connection at Kanduana T/W - II water supply scheme. |  |  | BILL/00175/2024-2025 | 102/JMD | 08/05/2024 |  | WBSEDCL | 5.18 | 0 | 0 | null
5 | JHARGRAM | Gopiballavpur - II | Jhargram Mechanical Division | KENDANA AND ADJOINING MOUJAS PWSS | SM/12346 | New | New Service connection charges. |  |  | BILL/00414/2024-2025 | 200/JMD | 14/06/2024 |  | WBSEDCL | 2.93 | 0 | 0 | 0
Total | [13 empty] | 33637.36 | 0 | 0