## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jhargram | Jhargram Division | CHAKKUA AND ADJOINING MOUJAS PWSS | SM/12356 | New | Laying distribution pipe line under JJM with allied work for CHAKKUA AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000071/2023-2024 | 1108/JHD | 18/07/2023 | 14/01/2024 | SUNIL DULE | 168.97 | 60.85 | 36.01 | 70
2 | JHARGRAM | Jhargram | Jhargram Division | CHAKKUA AND ADJOINING MOUJAS PWSS | SM/12356 | New | Sinking of Tube Well , Pump House , 100 cum CWR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Boundary wall, Installation of display Board, Operation and Maintenance and Accommodate FHTC ( 1104 nos) under JJM with allied work for CHAKKUA AND ITS ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour and materials within Jhargram Sub Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000072/2023-2024 | 1109/JHD | 18/07/2023 | 14/01/2024 | SUNIL DULE | 161.02 | 33.25 | 20.65 | 40
3 | JHARGRAM | Jhargram | Jhargram Division | CHAKKUA AND ADJOINING MOUJAS PWSS | SM/12356 | New | Construction of boundary wall and Allied works At Chakua, Uransol, Patharnala 1st and 2nd Tubewell site of public water supply schemes in Jhargram block within Jhargram District under Jhargram Division P.H.E Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000096/2024-2025 | 1281/JHD | 03/09/2024 | 03/10/2024 | SUNIL DULE | 37.46 | 0 | 0 | 0
4 | JHARGRAM | Jhargram | Jhargram Division | CHAKKUA AND ADJOINING MOUJAS PWSS | SM/12356 | New | Construction and commissioning of RCC Over Head Reservoir of capacity 150 cum and staging height 20 mtr. as per approved drawing with allied works of CHAKUA & its adjoining mouzas PWSS Proposed Pipe Water Supply Scheme for JHARGRAM Block, District: - Jhargram. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000383/2023-2024 | 2054/JHD | 07/12/2023 | 04/07/2024 | SATYABRATA BHAUMIK | 71.15 | 0 | 0 | 0
5 | JHARGRAM | Jhargram | Jhargram Division | CHAKKUA AND ADJOINING MOUJAS PWSS | SM/12356 | New | Material Requisition To Resource Division |  |  | RTOR000044/2023-2024 | 1563/JHD | 07/09/2023 |  | Resource Division | 32.14 | 0 | 0 | 0
6 | JHARGRAM | Jhargram | Jhargram Mechanical Division | CHAKKUA AND ADJOINING MOUJAS PWSS | SM/12356 | New | new service connection charges at Chakua water supply scheme |  |  | BILL/00020/2024-2025 | 19/JMD | 15/04/2024 |  | WBSEDCL | 5.29 | 0 | 0 | null
7 | JHARGRAM | Jhargram | Jhargram Mechanical Division | CHAKKUA AND ADJOINING MOUJAS PWSS | SM/12356 | New | New meter connection charges of Chakua-2 water supply scheme |  |  | BILL/00025/2024-2025 | 24/JMD | 22/04/2024 |  | WBSEDCL | 9.92 | 0 | 0 | null
8 | JHARGRAM | Jhargram | Jhargram Mechanical Division | CHAKKUA AND ADJOINING MOUJAS PWSS | SM/12356 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Chakkua & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M) | ORD/000068/2023-2024 | 1238/JMD | 26/05/2023 | 22/11/2023 | DEB KUMAR BASU | 20.83 | 7.09 | 34.05 | 50
Total | [13 empty] | 506.79 | 101.2 | 19.97