## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Gopiballavpur - I | Central Drilling | CHHAHAZARI HUMTIA AND ADJOINING MOUJAS PWSS | SM/12448 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2 | JHARGRAM | Gopiballavpur - I | Jhargram Division | CHHAHAZARI HUMTIA AND ADJOINING MOUJAS PWSS | SM/12448 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer,Assistant Engineer Headquarter | Junior Engineer, Gopiballavpur Sub Division,Junior Engineer-II | ORD/000298/2023-2024 | 1727/JHD | 30/09/2023 | 26/07/2024 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 0 | 0 | 25
3 | JHARGRAM | Gopiballavpur - I | Jhargram Division | CHHAHAZARI HUMTIA AND ADJOINING MOUJAS PWSS | SM/12448 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of Chhahazari Humtia and its adjoining mouzas Pipe Water Supply Scheme within Gopibalavpur-I Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division,Junior Engineer, Jhargram Division | ORD/000557/2023-2024 | 193/GPSD | 11/03/2024 | 10/04/2024 | BISHNU PADA NANDI | 4.28 | 2.08 | 48.56 | 95
4 | JHARGRAM | Gopiballavpur - I | Jhargram Division | CHHAHAZARI HUMTIA AND ADJOINING MOUJAS PWSS | SM/12448 | New | Material Requisition To Resource Division |  |  | RTOR000015/2023-2024 | 418/JHD | 13/03/2024 |  | Resource Division | 20.5 | 0 | 0 | 0
5 | JHARGRAM | Gopiballavpur - I | Jhargram Mechanical Division | CHHAHAZARI HUMTIA AND ADJOINING MOUJAS PWSS | SM/12448 | New | New Service Connection Charges for Chhayhazari Humita tw-I PWSS |  |  | BILL/01196/2023-2024 | 37/JMD | 01/02/2024 |  | WBSEDCL | 4.24 | 0 | 0 | null
Total | [13 empty] | 33653.55 | 2.08 | 0.01