## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Gopiballavpur - I | Central Drilling | BHILA AND ADJOINING MOUJAS PWSS | SM/12452 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2 | JHARGRAM | Gopiballavpur - I | Jhargram Division | BHILA AND ADJOINING MOUJAS PWSS | SM/12452 | New | Sinking of Tube Well under JJM with allied work for BHILA AND IT'S ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-I Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref: 1st Call eNIT_35 of 2022-23, SL No.-1) | Assistant Engineer | Junior Engineer-III | ORD/000046/2024-2025 | 1137/JHD | 06/08/2024 | 05/09/2024 | PALASH MANDAL | 16.67 | 0 | 0 | 0
3 | JHARGRAM | Gopiballavpur - I | Jhargram Division | BHILA AND ADJOINING MOUJAS PWSS | SM/12452 | New | Constructions of 150 cum OHR, soil investigation under JJM with allied work for BHILA AND IT'S ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-I Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer Gopiballavpur-I block | ORD/000278/2023-2024 | 1653/JHD | 15/09/2023 | 12/05/2024 | KANAN CONSTRUCTION ENTERPRISE | 73.16 | 12.08 | 16.51 | 70
4 | JHARGRAM | Gopiballavpur - I | Jhargram Division | BHILA AND ADJOINING MOUJAS PWSS | SM/12452 | New | Laying distribution pipe line under JJM with allied work for BHILA AND IT'S ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-I Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer Gopiballavpur-I block | ORD/000323/2023-2024 | 1857/JHD | 31/10/2023 | 28/04/2024 | ONKAR ENTERPRISE | 174.38 | 69.61 | 39.92 | 95
5 | JHARGRAM | Gopiballavpur - I | Jhargram Division | BHILA AND ADJOINING MOUJAS PWSS | SM/12452 | New | Rising main pipe line, Interconnection pipe line, Laying of Distribution pipe line, Installation of display Board, FHTC I 497 under JJM with allied work for BHILA AND IT'S ADJOINING I MOUJAS PWSS in GOPIBALLAVPUR-I Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref: 1st Call eNIT 35 of 2022-23, SL No.-4) | Assistant Engineer | Junior Engineer Gopiballavpur-I block | ORD/000330/2023-2024 | 1865/JHD | 01/11/2023 | 30/01/2024 | R.CONSTRUCTION | 59.84 | 19.5 | 32.59 | 95
6 | JHARGRAM | Gopiballavpur - I | Jhargram Division | BHILA AND ADJOINING MOUJAS PWSS | SM/12452 | New | Accommodate FHTC (700 nos) under JJM with allied work for BHILA AND IT'S ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-I Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref: 1st Call eNIT_35 of 2022-23, SL No.-6) | Assistant Engineer | Junior Engineer Gopiballavpur-I block,Junior Engineer, Gopiballavpur Sub Division | ORD/000355/2023-2024 | 1994/JHD | 01/12/2023 | 29/02/2024 | J.S.S. ENTERPRISE | 29.57 | 0 | 0 | 70
7 | JHARGRAM | Gopiballavpur - I | Jhargram Division | BHILA AND ADJOINING MOUJAS PWSS | SM/12452 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of Bhila and its adjoining mouzas Pipe Water Supply Scheme within Gopiballavpur-I Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000565/2023-2024 | 201/GPSD | 11/03/2024 | 10/04/2024 | J.S.S. ENTERPRISE | 4.3 | 0 | 0 | 0
8 | JHARGRAM | Gopiballavpur - I | Jhargram Division | BHILA AND ADJOINING MOUJAS PWSS | SM/12452 | New | Constructions of Pump House under JJM with allied work for BHILA AND IT'S ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-I Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 3rd Call (Ref: 1st Call eNIT_35 of EE/JHD of 2022-23, SL No.-2, 2nd Call eNIT_11 of EE/JHD of 2023-24, SL No.-3) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000568/2023-2024 | 435/JHD | 14/03/2024 | 12/06/2024 | MILON MAITY | 12.39 | 8.05 | 65.02 | 10
9 | JHARGRAM | Gopiballavpur - I | Jhargram Division | BHILA AND ADJOINING MOUJAS PWSS | SM/12452 | New | Material Requisition To Resource Division |  |  | RTOR000012/2023-2024 | 426/JHD | 13/03/2024 |  | Resource Division | 20.49 | 0 | 0 | 0
10 | JHARGRAM | Gopiballavpur - I | Jhargram Mechanical Division | BHILA AND ADJOINING MOUJAS PWSS | SM/12452 | New | Quotation for Bhila T/W - I water supply scheme. |  |  | BILL/01424/2023-2024 | 73/JMD | 15/03/2024 |  | WBSEDCL | 2.86 | 0 | 0 | null
11 | JHARGRAM | Gopiballavpur - I | Jhargram Mechanical Division | BHILA AND ADJOINING MOUJAS PWSS | SM/12452 | New | Quotation for Bhila T/W - 2 water supply scheme. |  |  | BILL/01425/2023-2024 | 74/JMD | 15/03/2024 |  | WBSEDCL | 3.96 | 0 | 0 | null
Total | [13 empty] | 21737.37 | 109.24 | 0.5