## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jamboni | Central Drilling | MAHISAMURA & ADJOINING MOUJAS PWSS | SM/12521 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2 | JHARGRAM | Jamboni | Jhargram Division | MAHISAMURA & ADJOINING MOUJAS PWSS | SM/12521 | New | Sinking of Tube Well , Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House & Providing Functional Household Tap Connection ( 7683 Nos), etc.including 02(Two) Years Operation & Maintenance For NOHARIA , SUSHNI, BAHIR GRAM, KAPGARI, MURAKATI, MAHISAMURA PWSS Pipe water supply Scheme within Jamboni Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division | ORD/000353/2023-2024 | 1954/JHD | 22/11/2023 | 19/07/2024 | SIBSANKAR CHOWDHURY | 2070.24 | 0 | 0 | 0
3 | JHARGRAM | Jamboni | Jhargram Division | MAHISAMURA & ADJOINING MOUJAS PWSS | SM/12521 | New | Construction of Boundary Wall & allied works at 2nd Tube well site of Mahismura and its adjoining mouzas pipe water supply Scheme within Jamboni Block under Jhargram RWS Sub Division within Jhargram Division. P.H.E. Dt (Total length 50 mtr, column size 250x250mm, M c/c ht. - 2.300 mtr from G.L.) | Assistant Engineer | The Junior Engineer-IV Jhargram Sub-Division | ORD/000583/2023-2024 | 519/JRWS | 15/03/2024 | 14/05/2024 | ENVOTECH INFRA SOLUTION | 4.77 | 0 | 0 | 0
4 | JHARGRAM | Jamboni | Jhargram Mechanical Division | MAHISAMURA & ADJOINING MOUJAS PWSS | SM/12521 | New | New Service connection |  |  | BILL/00406/2023-2024 | 1/JMD | 07/09/2023 |  | WBSEDCL | 1.38 | 0 | 0 | 0
5 | JHARGRAM | Jamboni | Jhargram Mechanical Division | MAHISAMURA & ADJOINING MOUJAS PWSS | SM/12521 | New | New Service connection |  |  | BILL/00663/2023-2024 | 12/JMD | 10/11/2023 |  | WBSEDCL | 1.26 | 0 | 0 | 0
Total | [13 empty] | 23417.41 | 0 | 0