## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jhargram | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/12777 | New | Sinking of Tube Well , Interconnection pipe line, Laying distribution pipe line, under JJM with allied work for RADHANAGAR AND ITS ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour and materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000014/2023-2024 | 649/JHD | 11/05/2023 | 09/08/2023 | R. CONSTRUCTION | 47.91 | 39.08 | 81.57 | 80
2 | JHARGRAM | Jhargram | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/12777 | New | Construction of Laying distribution pipe line under JJM with allied work for RADHANAGAR AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000019/2023-2024 | 815/JHD | 02/06/2023 | 31/08/2023 | SUNIL DULE | 94.39 | 41.33 | 43.79 | 88
3 | JHARGRAM | Jhargram | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/12777 | New | Accommodate FHTC ( 1591 nos) under JJM with allied work for RADHANAGAR AND ITS ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour and materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000028/2023-2024 | 858/JHD | 08/06/2023 | 06/09/2023 | SUNIL DULE | 67.72 | 16.63 | 24.56 | 40
4 | JHARGRAM | Jhargram | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/12777 | New | Construction of Pump House , Laying distribution pipe line, Boundary wall, Installation of display Board under JJM with allied work for RADHANAGAR AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. (2nd Call Ref eNIT_17 of 2022-23 , SL No.-3 ) | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000123/2023-2024 | 1322/JHD | 10/08/2023 | 08/11/2023 | R. CONSTRUCTION | 96.19 | 47.39 | 49.27 | 100
5 | JHARGRAM | Jhargram | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/12777 | New | Construction of 250 cum OHR, Rising main pipe line, Laying distribution pipe line, soil investigation under JJM with allied work for RADHANAGAR AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 3rd Call (Ref: 1 st Call eNIT_17 of 2022-23, SL No.-1 and 2nd Call eNIT_03 of 2023-24, SL No.-1) | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000294/2023-2024 | 1717/JHD | 29/09/2023 | 26/04/2024 | PARTHA PROTIM PRADHAN | 94.29 | 0 | 0 | 20
6 | JHARGRAM | Jhargram | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/12777 | New | Stagging of GI Pipe at Bindukata under Radhanagar PWSS under Jhargram Block under Jhargram District. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000461/2023-2024 | 341/JHD | 29/02/2024 | 30/03/2024 | A R CONSTRUCTION | 0.96 | 0.39 | 40 | 100
7 | JHARGRAM | Jhargram | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/12777 | New | Stagging of GI Pipe at Murgidihi, Kanyaduba under Radhanagar PWSS under Jhargram Block under Jhargram District. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000462/2023-2024 | 342/JHD | 29/02/2024 | 30/03/2024 | A R CONSTRUCTION | 0.91 | 0.36 | 40 | 100
8 | JHARGRAM | Jhargram | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/12777 | New | Material Requisition To Resource Division |  |  | RTOR000091/2023-2024 | 1591/JHD | 08/09/2023 |  | Resource Division | 60.65 | 0 | 0 | 0
9 | JHARGRAM | Jhargram | Jhargram Mechanical Division | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/12777 | New | New service connection |  |  | BILL/00389/2023-2024 | 27/AUG | 29/08/2023 |  | WBSEDCL | 6.24 | 0 | 0 | 0
10 | JHARGRAM | Jhargram | Jhargram Mechanical Division | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/12777 | New | New Service connection |  |  | BILL/00668/2023-2024 | 16/JMD | 10/11/2023 |  | WBSEDCL | 6.88 | 0 | 0 | 0
11 | JHARGRAM | Jhargram | Jhargram Mechanical Division | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/12777 | New | New service connection |  |  | BILL/01766/2023-2024 | 125/JMD | 29/03/2024 |  | WBSEDCL | 0.82 | 0 | 0 | 0
12 | JHARGRAM | Jhargram | Jhargram Mechanical Division | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/12777 | New | Supply, delivery, installation, commissioning & trial run operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Radhanagar & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M) | ORD/000045/2023-2024 | 1248/JMD | 26/05/2023 | 22/11/2023 | BEE GEE CONSTRUCTION | 21.86 | 8.95 | 40.95 | 65
Total | [13 empty] | 498.81 | 154.14 | 30.9