## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur - II | Jhargram Division | DHARAMPUR ZONE-VI CHANDPARA AND ADJOINING MOUJAS PWSS | SM/16994 | New | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House & Providing Functional Household Tap Connection (3149 Nos), etc. including 02(Two) Years Operation & Maintenance For DHARAMPUR ZONE-V , DHARAMPUR ZONE-VI Pipe water supply Scheme within Binpur-II Block Under Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer | Junior Engineer-II | ORD/000157/2023-2024 | 1396/JHD | 18/08/2023 | 05/03/2024 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 977.25 | 0 | 0 | 4
2 | JHARGRAM | Binpur - II | Jhargram Division | DHARAMPUR ZONE-VI CHANDPARA AND ADJOINING MOUJAS PWSS | SM/16994 | New | Material Requisition To Resource Division |  |  | RTOR000060/2023-2024 | 1598/JHD | 08/09/2023 |  | Resource Division | 55.79 | 0 | 0 | 0
3 | JHARGRAM | Binpur - II | Jhargram Mechanical Division | DHARAMPUR ZONE-VI CHANDPARA AND ADJOINING MOUJAS PWSS | SM/16994 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I, II & III and making compound lighting arrangement at T/W no. I of Dharampur zone-VI, Chandpara & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M) | ORD/000216/2023-2024 | 2282/JMD | 10/08/2023 | 06/02/2024 | DEBJYOTI BASU | 30.67 | 0 | 0 | 0
Total | [13 empty] | 1063.72 | 0 | 0