## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Gopiballavpur - I,Gopiballavpur - II | Central Drilling | GOHAL BURA AND ADJOINING MOUJAS PWSS | SM/17585 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2 | JHARGRAM | Gopiballavpur - I,Gopiballavpur - II | Jhargram Division | GOHAL BURA AND ADJOINING MOUJAS PWSS | SM/17585 | New | Construction of Laying distribution pipe line under JJM with allied work for GOHAL BURA AND ITS ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-I Block including supply of all labour and materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer-III | ORD/000039/2023-2024 | 865/JHD | 08/06/2023 | 06/09/2023 | ASIS KUMAR SARANGI | 30.88 | 26.04 | 84.34 | 85
3 | JHARGRAM | Gopiballavpur - I,Gopiballavpur - II | Jhargram Division | GOHAL BURA AND ADJOINING MOUJAS PWSS | SM/17585 | New | Construction of Laying distribution pipe line under JJM with allied work for GOHAL BURA AND IT'S ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-I Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. (Part-C) | Assistant Engineer | Junior Engineer-III | ORD/000046/2023-2024 | 866/JHD | 08/06/2023 | 06/09/2023 | ASIS KUMAR SARANGI | 66.32 | 47.09 | 71 | 75
4 | JHARGRAM | Gopiballavpur - I,Gopiballavpur - II | Jhargram Division | GOHAL BURA AND ADJOINING MOUJAS PWSS | SM/17585 | New | Construction of Laying distribution pipe line under JJM with allied work for GOHAL BURA AND IT'S ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-I Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. (Part-D) | Assistant Engineer | Junior Engineer-III | ORD/000049/2023-2024 | 867/JHD | 08/06/2023 | 06/09/2023 | ASIS KUMAR SARANGI | 61.58 | 49.33 | 80.1 | 75
5 | JHARGRAM | Gopiballavpur - I,Gopiballavpur - II | Jhargram Division | GOHAL BURA AND ADJOINING MOUJAS PWSS | SM/17585 | New | Construction of Laying distribution pipe line under JJM with allied work for GOHAL BURA AND IT'S ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-I Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref eNIT_24 of 2022-23 , SL No.-2 ) | Assistant Engineer | Junior Engineer-III | ORD/000159/2023-2024 | 1400/JHD | 18/08/2023 | 16/11/2023 | SRIMANTA KUMAR DE | 45.02 | 22.04 | 48.97 | 96
6 | JHARGRAM | Gopiballavpur - I,Gopiballavpur - II | Jhargram Division | GOHAL BURA AND ADJOINING MOUJAS PWSS | SM/17585 | New | Accommodate FHTC ( 1558 nos) under JJM with allied work for GOHAL BURA AND IT'S ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-I Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-III | ORD/000161/2023-2024 | 1401/JHD | 18/08/2023 | 16/11/2023 | M/S. D.K.H.CONSTRUCTION | 64.91 | 8.65 | 13.32 | 60
7 | JHARGRAM | Gopiballavpur - I,Gopiballavpur - II | Jhargram Division | GOHAL BURA AND ADJOINING MOUJAS PWSS | SM/17585 | New | Sinking of Tube Well , Pump House , 200 cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board, soil investigation under JJM with allied work for GOHAL BURA AND IT'S ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-I Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 3rd Call (Ref 1st Call eNIT_24 of 2022-23 , SL No.-1, 2nd Call eNIT_07 of 2023-24 , SL No.-3 ) | Assistant Engineer | Junior Engineer-III | ORD/000421/2023-2024 | 86/JHD | 17/01/2024 | 14/08/2024 | ANUSKA ENTERPRISE | 131.4 | 10.95 | 8.33 | 15
8 | JHARGRAM | Gopiballavpur - I,Gopiballavpur - II | Jhargram Division | GOHAL BURA AND ADJOINING MOUJAS PWSS | SM/17585 | New | Material Requisition To Resource Division |  |  | RTOR000076/2023-2024 | 1599/JHD | 08/09/2023 |  | Resource Division | 40.95 | 0 | 0 | 0
9 | JHARGRAM | Gopiballavpur - I,Gopiballavpur - II | Jhargram Mechanical Division | GOHAL BURA AND ADJOINING MOUJAS PWSS | SM/17585 | New | ADDITIONAL Quotation for new service connection at GOHALBURA T/W-II water supply scheme. |  |  | BILL/00174/2024-2025 | 101/JMD | 08/05/2024 |  | WBSEDCL | 3.32 | 0 | 0 | null
10 | JHARGRAM | Gopiballavpur - I,Gopiballavpur - II | Jhargram Mechanical Division | GOHAL BURA AND ADJOINING MOUJAS PWSS | SM/17585 | New | Supply of diesel and lubricants for KLR/DR/DTH-500 unit during PWSS works under JJM ( scheme code SM/17585 ) |  |  | BILL/01025/2024-2025 | null | 12/09/2024 |  | SURAJ SERVICE STATION | 0.8 | 0 | 0 | null
11 | JHARGRAM | Gopiballavpur - I,Gopiballavpur - II | Jhargram Mechanical Division | GOHAL BURA AND ADJOINING MOUJAS PWSS | SM/17585 | New | New Service connection charges. |  |  | BILL/01328/2023-2024 | 95/JMD | 22/02/2024 |  | WBSEDCL | 2.86 | 0 | 0 | 0
12 | JHARGRAM | Gopiballavpur - I,Gopiballavpur - II | Jhargram Mechanical Division | GOHAL BURA AND ADJOINING MOUJAS PWSS | SM/17585 | New | New Service connection charges. |  |  | BILL/01329/2023-2024 | 96/JMD | 22/02/2024 |  | WBSEDCL | 5.85 | 0 | 0 | 0
Total | [13 empty] | 21793.65 | 164.1 | 0.75