## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur - II | Bankura Mechanical | HIJLA AND ADJOINING MOUJAS PWSS | SM/17594 | New | Acceptance cum Formal work order for the work of Supply and delivery of different types of Drilling Martials in connection with Jal Jeevan Mission Program at Jhargram under Bankura Mechanical Division P.H.E Dte | Assistant Engineer |  | ORD/000577/2023-2024 | 2038/BMD | 01/09/2023 | 31/10/2023 | CHAKRABORTY MINING & ENGINEERING. | 22.91 | 11.45 | 50 | 100
2 | JHARGRAM | Binpur - II | Bankura Mechanical | HIJLA AND ADJOINING MOUJAS PWSS | SM/17594 | New | Acceptance cum Formal work order for the work of Providing man power engagement and Driver for construction of R.B.T.W. in connection to JJM programme in Jhargram District by Rig unit KLR at B.M.S.D (D) under Bankura Mechanical Division PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000756/2023-2024 | 948/BMSD(D) | 17/11/2023 | 02/12/2023 | CHAKRABORTY MINING & ENGINEERING. | 0.8 | 0 | 0 | 100
3 | JHARGRAM | Binpur - II | Bankura Mechanical | HIJLA AND ADJOINING MOUJAS PWSS | SM/17594 | New | Acceptance cum Formal work order for the work of Providing man power engagement and Driver for construction of R.B.T.W in connection to JJM Programme in Jhargram District by Rig unit KLR at B.M.S.D(D) under B.M.D., P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/000794/2023-2024 | 984/BMSD(D) | 01/12/2023 | 16/12/2023 | CHAKRABORTY MINING & ENGINEERING. | 0.8 | 0 | 0 | 100
4 | JHARGRAM | Binpur - II | Bankura Mechanical | HIJLA AND ADJOINING MOUJAS PWSS | SM/17594 | New | Acceptance cum Formal work order for the work of Yield testing of different Departmentally drilling site in Bhelaidiha GP of Binpur-II Block of Jhargram District in Connection to JJM programme under Bankura Mechanical Division P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/001022/2023-2024 | 20/BMSD(D) | 05/01/2024 | 25/01/2024 | DEBJYOTI BASU | 0.97 | 0.48 | 50 | 100
5 | JHARGRAM | Binpur - II | Bankura Mechanical | HIJLA AND ADJOINING MOUJAS PWSS | SM/17594 | New | Acceptance cum Formal work order for the work of Providing man power engagement and Driver for construction of R.B.T.W in connection to JJM programme in Jhargram District by Rig unit KLR at B.M.S.D(D) under B.M.D., P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/001103/2023-2024 | 1028/BMSD(D) | 15/12/2023 | 30/12/2023 | CHAKRABORTY MINING & ENGINEERING. | 0.8 | 0 | 0 | 100
6 | JHARGRAM | Binpur - II | Bankura Mechanical | HIJLA AND ADJOINING MOUJAS PWSS | SM/17594 | New | Acceptance cum Formal work order for the work of Providing man power engagement and Driver for construction of R.B.T.W in connection to JJM programme in Jhargram District by Rig unit KLR at B.M.S.D(D) under Bankura Mechanical Division P.H.E. Dte | Driller-in-Charge | Junior Engineer | ORD/001195/2023-2024 | 101/BMSD(D) | 31/01/2024 | 15/02/2024 | CHAKRABORTY MINING & ENGINEERING. | 0.8 | 0 | 0 | 73
7 | JHARGRAM | Binpur - II | Bankura Mechanical | HIJLA AND ADJOINING MOUJAS PWSS | SM/17594 | New | Acceptance cum Formal work order for the work of Yield testing of different Departmentally drilling pin point place of Banksol, Barasol, Mahulbani, Hijla, Bansgar, Adgari etc site in Bhelaidiha gp, Binpur-II Block of Jhargram District in connection to JJM programme under Bankura Mechanical Division, P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/001246/2023-2024 | 250/BMSD(D) | 13/03/2024 | 11/07/2024 | DEBJYOTI BASU | 0.97 | 0 | 0 | 100
8 | JHARGRAM | Binpur - II | Bankura Mechanical | HIJLA AND ADJOINING MOUJAS PWSS | SM/17594 | New | Acceptance cum Formal work order for the work of Providing man power engagement and Driver for construction of R.B.T.W in connection to JJM Programme in Jhargram District by Rig unit KLR at B.M.S.D(D) under B.M.D, P.H.E Dte. | Driller-in-Charge | Junior Engineer | ORD/001278/2023-2024 | 254/BMSD(D) | 14/03/2024 | 29/03/2024 | CHAKRABORTY MINING & ENGINEERING. | 0.8 | 0 | 0 | 0
9 | JHARGRAM | Binpur - II | Bankura Mechanical | HIJLA AND ADJOINING MOUJAS PWSS | SM/17594 | New | Acceptance cum Formal work order for the work of Providing man power engagement and Driver for construction of R.B.T.W in connection to JJM Programme in Jhargram District by Rig unit KLR at B.M.S.D(D) under B.M.D, P.H.E Dte. | Driller-in-Charge | Junior Engineer | ORD/001279/2023-2024 | 264/BMSD(D) | 15/03/2024 | 30/03/2024 | CHAKRABORTY MINING & ENGINEERING. | 0.8 | 0 | 0 | 0
10 | JHARGRAM | Binpur - II | Bankura Mechanical | HIJLA AND ADJOINING MOUJAS PWSS | SM/17594 | New | Acceptance cum Formal work order for the work of Supply, Delivery and Fitting fixing of Battery for Rig unit 31D and its Compressor unit for Jhargram JJM drilling program under B.M.S.D(D), under B.M.D. P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/001282/2023-2024 | 261/BMSD(D) | 15/03/2024 | 25/03/2024 | M/S NABIN GOPAL SENGUPTA | 0.83 | 0 | 0 | 0
11 | JHARGRAM | Binpur - II | Jhargram Division | HIJLA AND ADJOINING MOUJAS PWSS | SM/17594 | New | Supply and Delivery of fuel(Diesel) and lubricants to Departmental Rig unit(KLR) and supporting vehicle(WB 67 6943) for drilling works in connection of Jhargram JJM programme under BMSD(D) PHE Dte. |  |  | BILL/00219/2024-2025 | null | 23/07/2024 |  | LALJI RAJA & SONS AGENCIES | 1.55 | 0 | 0 | null
12 | JHARGRAM | Binpur - II | Jhargram Division | HIJLA AND ADJOINING MOUJAS PWSS | SM/17594 | New | Supply and Delivery of fuel(Diesel) and lubricants to Departmental Rig unit(KLR) and supporting vehicle(WB 67 6943) for drilling works in connection of Jhargram JJM programme under BMSD(D) PHE Dte. |  |  | BILL/00220/2024-2025 | null | 23/07/2024 |  | LALJI RAJA & SONS AGENCIES | 1.61 | 0 | 0 | null
13 | JHARGRAM | Binpur - II | Jhargram Division | HIJLA AND ADJOINING MOUJAS PWSS | SM/17594 | New | Supply and Delivery of fuel(Diesel) and lubricants to Departmental Rig unit(KLR) and supporting vehicle(WB 67 6943) for drilling works in connection of Jhargram JJM programme under BMSD(D) PHE Dte. |  |  | BILL/00221/2024-2025 | null | 23/07/2024 |  | LALJI RAJA & SONS AGENCIES | 3.1 | 0 | 0 | null
14 | JHARGRAM | Binpur - II | Jhargram Mechanical Division | HIJLA AND ADJOINING MOUJAS PWSS | SM/17594 | New | New service connection charges |  |  | BILL/01076/2023-2024 | 11/JMD | 05/01/2024 |  | WBSEDCL | 1.05 | 0 | 0 | 0
15 | JHARGRAM | Binpur - II | Jhargram Mechanical Division | HIJLA AND ADJOINING MOUJAS PWSS | SM/17594 | New | New connection bill for Jagannathpur in Bheliadiha GP |  |  | BILL/01473/2023-2024 | 75/JMD | 20/03/2024 |  | WBSEDCL | 0.21 | 0 | 0 | null
16 | JHARGRAM | Binpur - II | Jhargram Mechanical Division | HIJLA AND ADJOINING MOUJAS PWSS | SM/17594 | New | New connection bill for Mahulbani in Bheliadiha GP |  |  | BILL/01474/2023-2024 | 76/JMD | 20/03/2024 |  | WBSEDCL | 0.21 | 0 | 0 | null
17 | JHARGRAM | Binpur - II | Jhargram Mechanical Division | HIJLA AND ADJOINING MOUJAS PWSS | SM/17594 | New | Erection & commissioning of 22 (twenty two) nos. standalone piped water supply schemes by constructing pump house, community tank, laying of distribution pipeline for providing FHTC with supply, delivery and installation of pumping machineries & allied Electro-Mechanical accessories at Bhelaidiha G.P. in place of (Chainbera Zone-III Joypur (TSM/015566), Hijla (TSM/014334) and Banksol (TSM/015563) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | DIC(D)_MMSD(D) | Junior Engineer | ORD/000322/2023-2024 | 3015/JMD | 20/10/2023 | 17/02/2024 | CONCORD ENGINEERING | 621.67 | 21.89 | 3.52 | 10
18 | JHARGRAM | Binpur - II | Jhargram Mechanical Division | HIJLA AND ADJOINING MOUJAS PWSS | SM/17594 | New | Supply & delivery of different spare parts for LMP-500 and other departmental Rig unit at MMSD(D) store under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000729/2024-2025 | 572/W/MMSD(D) | 04/07/2024 | 11/07/2024 | B. P. TRADING CORPORATION | 0.97 | 0 | 0 | 0
19 | JHARGRAM | Binpur - II | Jhargram Mechanical Division | HIJLA AND ADJOINING MOUJAS PWSS | SM/17594 | New | Supply & delivery of Hydraulic house and other essential spare parts at MMSD(D) store under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000730/2024-2025 | 573/W/MMSD(D) | 04/07/2024 | 11/07/2024 | B. P. TRADING CORPORATION | 0.97 | 0 | 0 | 0
20 | JHARGRAM | Binpur - II | Jhargram Mechanical Division | HIJLA AND ADJOINING MOUJAS PWSS | SM/17594 | New | Supply & delivery of essential drilling tools and Mud pump spare parts for 21D/ LT-500 and KLR/DR/DTH-500 under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000731/2024-2025 | 574/W/MMSD(D) | 04/07/2024 | 11/07/2024 | B. P. TRADING CORPORATION | 0.99 | 0 | 0 | 0
21 | JHARGRAM | Binpur - II | Jhargram Mechanical Division | HIJLA AND ADJOINING MOUJAS PWSS | SM/17594 | New | Supply & delivery of Mud Rotary Drilling tools at MMSD(D) store of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000733/2024-2025 | 576/W/MMSD(D) | 04/07/2024 | 11/07/2024 | B. P. TRADING CORPORATION | 0.77 | 0 | 0 | 0
Total | [13 empty] | 663.57 | 33.83 | 5.1