## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur - II | Jhargram Division | RAGHUNATHPUR AND ADJOINING MOUJAS PWSS | SM/17595 | New | New Service Connection Charges for Majugora, Raghunatpur & Adjoining Moujas PWSS |  |  | BILL/00146/2024-2025 | BP-2024-25-111 | 10/07/2024 |  | WBSEDCL | 0.21 | 0 | 0 | null
2 | JHARGRAM | Binpur - II | Jhargram Division | RAGHUNATHPUR AND ADJOINING MOUJAS PWSS | SM/17595 | New | New Service Connection Charges for Phulgeria, Raghunatpur & Adjoining Moujas PWSS |  |  | BILL/00147/2024-2025 | BP-2024-25-111 | 10/07/2024 |  | WBSEDCL | 0.21 | 0 | 0 | null
3 | JHARGRAM | Binpur - II | Jhargram Division | RAGHUNATHPUR AND ADJOINING MOUJAS PWSS | SM/17595 | New | New Service Connection Charges for Raghunathpur, Raghunatpur & Adjoining Moujas PWSS |  |  | BILL/00150/2024-2025 | BP-2024-25-111 | 10/07/2024 |  | WBSEDCL | 0.21 | 0 | 0 | null
4 | JHARGRAM | Binpur - II | Jhargram Division | RAGHUNATHPUR AND ADJOINING MOUJAS PWSS | SM/17595 | New | New Service Connection Charges for Dangardiha, Raghunatpur & Adjoining Moujas PWSS |  |  | BILL/00151/2024-2025 | BP-2024-25-111 | 10/07/2024 |  | WBSEDCL | 0.21 | 0 | 0 | null
5 | JHARGRAM | Binpur - II | Jhargram Division | RAGHUNATHPUR AND ADJOINING MOUJAS PWSS | SM/17595 | New | New Service Connection Charges for Jamjurki, Raghunatpur & Adjoining Moujas PWSS |  |  | BILL/00152/2024-2025 | BP-2024-25-111 | 10/07/2024 |  | WBSEDCL | 0.21 | 0 | 0 | null
6 | JHARGRAM | Binpur - II | Jhargram Division | RAGHUNATHPUR AND ADJOINING MOUJAS PWSS | SM/17595 | New | New Service Connection Charges for Adargeria, Raghunatpur & Adjoining Moujas PWSS |  |  | BILL/00153/2024-2025 | BP-2024-25-111 | 10/07/2024 |  | WBSEDCL | 0.21 | 0 | 0 | null
7 | JHARGRAM | Binpur - II | Jhargram Division | RAGHUNATHPUR AND ADJOINING MOUJAS PWSS | SM/17595 | New | 33 nos. Stand Alone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for BHULAVEDA GP ( TALPUPUKHURIA ,RAGHUNATHPUR ,GIDIGHATI ,SHIYARBINDA PWSS) under Binpur-II Block under Jhargram Division, PHE dte. (2nd Call Ref eNIT_36 of 2022-23 , SL No.-2 ) | Assistant Engineer | Junior Engineer-II | ORD/000190/2023-2024 | 1531/JHD | 06/09/2023 | 04/01/2024 | ASIS KUMAR SARANGI | 910.58 | 0 | 0 | 40
8 | JHARGRAM | Binpur - II | Jhargram Division | RAGHUNATHPUR AND ADJOINING MOUJAS PWSS | SM/17595 | New | 66 nos. Sinking of 125mm x 115mm x 200m Deep Tube wells by DTH method for installation of Submersible Pumping machinery for BHULAVEDA GP (TALPUPUKHURIA, RAGHUNATHPUR, GIDIGHATI, SHIYARBINDA PWSS) under Binpur-II Block under Jhargram Division, PHE dte. 2nd Call (Ref: 1st Call eNIT_38 of 2022-23, SL No.-2) | Assistant Engineer | Junior Engineer-II | ORD/000314/2023-2024 | 1834/JHD | 27/10/2023 | 26/12/2023 | SUNIL DULE | 108.48 | 0 | 0 | 60
9 | JHARGRAM | Binpur - II | Jhargram Division | RAGHUNATHPUR AND ADJOINING MOUJAS PWSS | SM/17595 | New | Four numbers (4) of yield test process need to be done at Jamjurki & Phulgeria of Bhulaveda GP of Binpur II Block, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000652/2023-2024 | 500/JRWS | 15/03/2024 | 14/04/2024 | SUNIL DULE | 0.72 | 0 | 0 | 0
10 | JHARGRAM | Binpur - II | Jhargram Division | RAGHUNATHPUR AND ADJOINING MOUJAS PWSS | SM/17595 | New | Four numbers (4) of yield test process need to be done at Dangardiha & Birgi of Bhulaveda GP of Binpur II Block, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000653/2023-2024 | 501/JRWS | 15/03/2024 | 14/04/2024 | SUNIL DULE | 0.72 | 0 | 0 | 0
11 | JHARGRAM | Binpur - II | Jhargram Division | RAGHUNATHPUR AND ADJOINING MOUJAS PWSS | SM/17595 | New | Four numbers (4) of yield test process need to be done at Raghunathpur & Adargeria of Bhulaveda GP of Binpur II Block, under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000661/2023-2024 | 509/JRWS | 15/03/2024 | 14/04/2024 | SUNIL DULE | 0.72 | 0 | 0 | 0
12 | JHARGRAM | Binpur - II | Jhargram Mechanical Division | RAGHUNATHPUR AND ADJOINING MOUJAS PWSS | SM/17595 | New | New Service Connection Charges for Raghunatpur & Adjoining Moujas PWSS Birgi |  |  | BILL/00433/2024-2025 | null | 18/06/2024 |  | WBSEDCL | 0.21 | 0 | 0 | null
Total | [13 empty] | 1022.68 | 0 | 0