## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur - II | Jhargram Mechanical Division | CHAINBERA ZONE-ll JARDA AND IT'S ADJOINING MOUJAS PWSS | SM/17925 | New | Supply of diesel and lubricants for KLR/DR/DTH-500 unit during PWSS works under JJM. |  |  | BILL/00318/2024-2025 | 134/JMD | 24/05/2024 |  | SURAJ SERVICE STATION | 1.01 | 0 | 0 | null
2 | JHARGRAM | Binpur - II | Jhargram Mechanical Division | CHAINBERA ZONE-ll JARDA AND IT'S ADJOINING MOUJAS PWSS | SM/17925 | New | New service connection charges |  |  | BILL/00852/2023-2024 | 32/JMD | 19/12/2023 |  | WBSEDCL | 1.68 | 0 | 0 | 0
3 | JHARGRAM | Binpur - II | Jhargram Mechanical Division | CHAINBERA ZONE-ll JARDA AND IT'S ADJOINING MOUJAS PWSS | SM/17925 | New | New Service connection |  |  | BILL/00871/2023-2024 | 44/JMD | 29/12/2023 |  | WBSEDCL | 1.26 | 0 | 0 | 0
4 | JHARGRAM | Binpur - II | Jhargram Mechanical Division | CHAINBERA ZONE-ll JARDA AND IT'S ADJOINING MOUJAS PWSS | SM/17925 | New | New Service connection charges. |  |  | BILL/01347/2023-2024 | 10/JMD | 01/03/2024 |  | WBSEDCL | 0.42 | 0 | 0 | 0
5 | JHARGRAM | Binpur - II | Jhargram Mechanical Division | CHAINBERA ZONE-ll JARDA AND IT'S ADJOINING MOUJAS PWSS | SM/17925 | New | Supply & delivery of upvc consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicle for Dept. Rig unit for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH / combination method at Jamirdiha & its adjacent nine (09) nos. villages under ¿Ergoda¿ G.P. in place of {Chainbera Zone-III Joypur (TSM/015566)} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | Driller-In-Charge | Junior Engineer | ORD/000056/2023-2024 | 1350/JMD | 06/06/2023 | 16/07/2023 | SUBHASIS ROY | 22 | 3.15 | 14.31 | 30
6 | JHARGRAM | Binpur - II | Jhargram Mechanical Division | CHAINBERA ZONE-ll JARDA AND IT'S ADJOINING MOUJAS PWSS | SM/17925 | New | Construction of (125 mm X 115 mm X 200 mtr.) RBTW by DTH/ combination method for providing FHTC at SITAPUR & its adjacent Seventy Three (73) nos. villages under Sandapara G.P. in place of (Chainbera Zone-I Darra (TSM/015763), Chainbera Zone-II Jarda (TSM/015919) and Chainbera Zone-III Joypur (TSM/015566) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | Driller-In-Charge | Junior Engineer | ORD/000223/2023-2024 | 2297/JMD | 11/08/2023 | 06/01/2024 | MONDAL PRECISION PRIVATE LIMITED | 163.47 | 60.22 | 36.84 | 100
7 | JHARGRAM | Binpur - II | Jhargram Mechanical Division | CHAINBERA ZONE-ll JARDA AND IT'S ADJOINING MOUJAS PWSS | SM/17925 | New | Erection & commissioning of 37 (thirty seven) nos. standalone piped water supply schemes by constructing pump house, community tank, laying of distribution pipeline for providing FHTC with supply, delivery and installation of pumping machineries & allied Electro-Mechanical accessories at Sandapara G.P. in place of (Chainbera Zone-I Darra (TSM/015763), Chainbera Zone-II Jarda (TSM/015919) and Chainbera Zone-III Joypur (TSM/015566) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | Driller-In-Charge | Junior Engineer | ORD/000227/2023-2024 | 2303/JMD | 14/08/2023 | 12/12/2023 | CONCORD ENGINEERING | 1025.92 | 40.37 | 3.94 | 12
Total | [13 empty] | 1215.75 | 103.74 | 8.53