## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur - II | Jhargram Division | DAKAI AND ADJOINING MOUJAS PWSS | SM/17927 | New | New Service Connection Charges for Bodadihi Dakai & Adjoining Moujas PWSS |  |  | BILL/00158/2024-2025 | BP-2024-25-111 | 10/07/2024 |  | WBSEDCL | 0.21 | 0 | 0 | null
2 | JHARGRAM | Binpur - II | Jhargram Division | DAKAI AND ADJOINING MOUJAS PWSS | SM/17927 | New | New Service Connection Charges for Kankrijharna, Dakai & Adjoining Moujas PWSS |  |  | BILL/00174/2024-2025 | BP-2024-25-111 | 10/07/2024 |  | WBSEDCL | 0.21 | 0 | 0 | null
3 | JHARGRAM | Binpur - II | Jhargram Division | DAKAI AND ADJOINING MOUJAS PWSS | SM/17927 | New | New Service Connection Charges for Dakai, Dakai & Adjoining Moujas PWSS |  |  | BILL/00175/2024-2025 | BP-2024-25-111 | 10/07/2024 |  | WBSEDCL | 0.21 | 0 | 0 | null
4 | JHARGRAM | Binpur - II | Jhargram Division | DAKAI AND ADJOINING MOUJAS PWSS | SM/17927 | New | New Service Connection Charges for Labani, Dakai & Adjoining Moujas PWSS |  |  | BILL/00176/2024-2025 | BP-2024-25-111 | 10/07/2024 |  | WBSEDCL | 0.21 | 0 | 0 | null
5 | JHARGRAM | Binpur - II | Jhargram Division | DAKAI AND ADJOINING MOUJAS PWSS | SM/17927 | New | 31 nos. Stand Alone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for SIMULPAL GP (GAJPATHAR, DAKAI, BIRMADAL, BURIJHOR PWSS) under Binpur II Block under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000292/2023-2024 | 1714/JHD | 29/09/2023 | 27/01/2024 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 848.26 | 0 | 0 | 30
6 | JHARGRAM | Binpur - II | Jhargram Division | DAKAI AND ADJOINING MOUJAS PWSS | SM/17927 | New | 62 nos. Sinking of 125mm x 115mm x 200m Deep Tube wells by DTH method for installation of Submersible Pumping machinery for SIMULPAL GP (GAJPATHAR, DAKAI, BIRMADAL, BURIJHOR PWSS) under Binpur-II Block under Jhargram Division, PHE dte. 2nd Call (Ref: 1st Call eNIT_38 of 2022-23, SL No.-4) | Assistant Engineer | Junior Engineer-II | ORD/000315/2023-2024 | 1835/JHD | 27/10/2023 | 26/12/2023 | ASIS KUMAR SARANGI | 101.91 | 4.18 | 4.1 | 80
7 | JHARGRAM | Binpur - II | Jhargram Division | DAKAI AND ADJOINING MOUJAS PWSS | SM/17927 | New | Four numbers (4) of yield test process need to be done at Dakai & Kankrijharna of Simulpal GP of Binpur II Block, under Jhargram division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000672/2023-2024 | 538/JRWS | 16/03/2024 | 15/04/2024 | ASSOCIATED ENGINEERS & TRADERS | 0.72 | 0 | 0 | 100
8 | JHARGRAM | Binpur - II | Jhargram Division | DAKAI AND ADJOINING MOUJAS PWSS | SM/17927 | New | Four numbers (4) of yield test process need to be done at Jarma & Labani of Sumulpal GP of Simulpal Block, under Jhargram division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000673/2023-2024 | 539/JRWS | 16/03/2024 | 15/04/2024 | ASSOCIATED ENGINEERS & TRADERS | 0.72 | 0 | 0 | 100
9 | JHARGRAM | Binpur - II | Jhargram Division | DAKAI AND ADJOINING MOUJAS PWSS | SM/17927 | New | Four numbers (4) of yield test process need to be done at Bodadihi & Machhkandna of Simulpal GP of Binpur II Block, under Jhargram division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000674/2023-2024 | 540/JRWS | 16/03/2024 | 15/04/2024 | ASSOCIATED ENGINEERS & TRADERS | 0.72 | 0 | 0 | 100
Total | [13 empty] | 953.16 | 4.18 | 0.44