## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur - II | Jhargram Division | BURIJHOR AND ADJOINING MOUJAS PWSS | SM/17928 | New | New Service Connection Charges for kodamdiha Burijhor & Adjoining Moujas PWSS |  |  | BILL/00169/2024-2025 | BP-2024-25-111 | 10/07/2024 |  | WBSEDCL | 0.21 | 0 | 0 | null
2 | JHARGRAM | Binpur - II | Jhargram Division | BURIJHOR AND ADJOINING MOUJAS PWSS | SM/17928 | New | New Service Connection Charges for Burijhor, Burijhor & Adjoining Moujas PWSS |  |  | BILL/00177/2024-2025 | BP-2024-25-111 | 10/07/2024 |  | WBSEDCL | 0.21 | 0 | 0 | null
3 | JHARGRAM | Binpur - II | Jhargram Division | BURIJHOR AND ADJOINING MOUJAS PWSS | SM/17928 | New | New Service Connection Charges for Singaduba, Burijhor & Adjoining Moujas PWSS |  |  | BILL/00178/2024-2025 | BP-2024-25-111 | 10/07/2024 |  | WBSEDCL | 0.21 | 0 | 0 | null
4 | JHARGRAM | Binpur - II | Jhargram Division | BURIJHOR AND ADJOINING MOUJAS PWSS | SM/17928 | New | New Service Connection Charges for Shusnijubi, Burijhor & Adjoining Moujas PWSS |  |  | BILL/00179/2024-2025 | BP-2024-25-111 | 10/07/2024 |  | WBSEDCL | 0.21 | 0 | 0 | null
5 | JHARGRAM | Binpur - II | Jhargram Division | BURIJHOR AND ADJOINING MOUJAS PWSS | SM/17928 | New | New Service Connection Charges for Pirragerya, Burijhor & Adjoining Moujas PWSS |  |  | BILL/00180/2024-2025 | BP-2024-25-111 | 10/07/2024 |  | WBSEDCL | 0.21 | 0 | 0 | null
6 | JHARGRAM | Binpur - II | Jhargram Division | BURIJHOR AND ADJOINING MOUJAS PWSS | SM/17928 | New | New Service Connection Charges for Dhangikusum, Burijhor & Adjoining Moujas PWSS |  |  | BILL/00181/2024-2025 | BP-2024-25-111 | 10/07/2024 |  | WBSEDCL | 0.21 | 0 | 0 | null
7 | JHARGRAM | Binpur - II | Jhargram Division | BURIJHOR AND ADJOINING MOUJAS PWSS | SM/17928 | New | 31 nos. Stand Alone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for SIMULPAL GP (GAJPATHAR, DAKAI, BIRMADAL, BURIJHOR PWSS) under Binpur II Block under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000292/2023-2024 | 1714/JHD | 29/09/2023 | 27/01/2024 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 848.26 | 0 | 0 | 30
8 | JHARGRAM | Binpur - II | Jhargram Division | BURIJHOR AND ADJOINING MOUJAS PWSS | SM/17928 | New | 62 nos. Sinking of 125mm x 115mm x 200m Deep Tube wells by DTH method for installation of Submersible Pumping machinery for SIMULPAL GP (GAJPATHAR, DAKAI, BIRMADAL, BURIJHOR PWSS) under Binpur-II Block under Jhargram Division, PHE dte. 2nd Call (Ref: 1st Call eNIT_38 of 2022-23, SL No.-4) | Assistant Engineer | Junior Engineer-II | ORD/000315/2023-2024 | 1835/JHD | 27/10/2023 | 26/12/2023 | ASIS KUMAR SARANGI | 101.91 | 0 | 0 | 80
9 | JHARGRAM | Binpur - II | Jhargram Division | BURIJHOR AND ADJOINING MOUJAS PWSS | SM/17928 | New | Two numbers (2) of yield test process need to be done at Dhangikusum of Simulpal GP of Binpur II Block, under Jhargram division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000663/2023-2024 | 529/JRWS | 16/03/2024 | 15/04/2024 | ASSOCIATED ENGINEERS & TRADERS | 0.36 | 0 | 0 | 100
10 | JHARGRAM | Binpur - II | Jhargram Division | BURIJHOR AND ADJOINING MOUJAS PWSS | SM/17928 | New | Four numbers (4) of yield test process need to be done at Shushnijubi & Banspahari of Simulpal GP of Binpur II Block, under Jhargram division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000664/2023-2024 | 530/JRWS | 16/03/2024 | 15/04/2024 | ASSOCIATED ENGINEERS & TRADERS | 0.72 | 0 | 0 | 100
11 | JHARGRAM | Binpur - II | Jhargram Division | BURIJHOR AND ADJOINING MOUJAS PWSS | SM/17928 | New | Four numbers (4) of yield test process need to be done at Burijhor & Singaduba of Simulpal GP of Binpur II Block, under Jhargram division, PHE Dte | Assistant Engineer | Junior Engineer-II | ORD/000665/2023-2024 | 531/JRWS | 16/03/2024 | 15/04/2024 | ASSOCIATED ENGINEERS & TRADERS | 0.72 | 0 | 0 | 100
12 | JHARGRAM | Binpur - II | Jhargram Division | BURIJHOR AND ADJOINING MOUJAS PWSS | SM/17928 | New | Four numbers (4) of yield test process need to be done at Kadamdiha & Pirragerya of Simulpal GP of Binpur II Block, under Jhargram division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000666/2023-2024 | 532/JRWS | 16/03/2024 | 15/04/2024 | ASSOCIATED ENGINEERS & TRADERS | 0.72 | 0 | 0 | 100
Total | [13 empty] | 953.94 | 0 | 0