## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur - II | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS | SM/17929 | New | Providing fuel & lubricant for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary Method at Mohanpur & adjacent seven (07) nos. villages under Kanko G.P. in place of {Dharampur Zone-III Kanko (TSM/015873)} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. |  |  | BILL/01134/2023-2024 | 17/JMD | 10/01/2024 |  | SURAJ SERVICE STATION | 0.89 | 0 | 0 | 0
2 | JHARGRAM | Binpur - II | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS | SM/17929 | New | New Service connection charges. |  |  | BILL/01140/2023-2024 | 21/JMD | 11/01/2024 |  | WBSEDCL | 1.47 | 0 | 0 | 0
3 | JHARGRAM | Binpur - II | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS | SM/17929 | New | New service connection charge in Nachna, Kanko GP, Binpur-1 |  |  | BILL/01206/2023-2024 | 44/JMD | 06/02/2024 |  | WBSEDCL | 0.21 | 0 | 0 | null
4 | JHARGRAM | Binpur - II | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS | SM/17929 | New | New service connection charge in Salpatra, Kanko GP, Binpur-1 |  |  | BILL/01207/2023-2024 | 44/JMD | 06/02/2024 |  | WBSEDCL | 0.21 | 0 | 0 | null
5 | JHARGRAM | Binpur - II | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS | SM/17929 | New | New service connection charges for Bankrasol, Kanko GP ,Jhargram |  |  | BILL/01316/2023-2024 | 67/JMD | 12/02/2024 |  | WBSEDCL | 0.21 | 0 | 0 | null
6 | JHARGRAM | Binpur - II | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS | SM/17929 | New | New service connection charges for Jadabpur, Kanko GP ,Jhargram |  |  | BILL/01317/2023-2024 | 67/JMD | 12/02/2024 |  | WBSEDCL | 0.21 | 0 | 0 | null
7 | JHARGRAM | Binpur - II | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS | SM/17929 | New | Providing fuel & lubricant for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary Method at Mohanpur & adjacent seven (07) nos. villages under Kanko G.P. in place of {Dharampur Zone-III Kanko (TSM/015873)} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. |  |  | BILL/01323/2023-2024 | 91/JMD | 16/02/2024 |  | SURAJ SERVICE STATION | 1.25 | 0 | 0 | 0
8 | JHARGRAM | Binpur - II | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS | SM/17929 | New | Providing fuel & lubricant for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary Method at Kanko G.P. in place of {Dharampur Zone-III Kanko } w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. |  |  | BILL/01349/2023-2024 | 12/JMD | 01/03/2024 |  | SURAJ SERVICE STATION | 1.23 | 0 | 0 | 0
9 | JHARGRAM | Binpur - II | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS | SM/17929 | New | Supply & delivery of upvc consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicle for Dept. Rig unit for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary Method at Mohanpur & adjacent seven (07) nos. villages under ¿Kanko¿ G.P. in place of {Dharampur Zone-III Kanko (TSM/015873)} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | Driller-In-Charge | Junior Engineer | ORD/000022/2023-2024 | 1126/JMD | 18/05/2023 | 19/06/2023 | RSA ENTERPRISE | 27 | 17.92 | 66.36 | 85
10 | JHARGRAM | Binpur - II | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS | SM/17929 | New | Supply & delivery of upvc consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicle for Dept. Rig unit for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary Method at Bankrasol & adjacent eight (08) nos. villages under ¿Kanko¿ G.P. in place of {Dharampur Zone-III Kanko (TSM/015873)} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | Driller-In-Charge | Junior Engineer | ORD/000023/2023-2024 | 1127/JMD | 18/05/2023 | 23/06/2023 | RSA ENTERPRISE | 30.38 | 21.76 | 71.64 | 82
11 | JHARGRAM | Binpur - II | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS | SM/17929 | New | Erection & commissioning of 23 (twenty three) nos. standalone piped water supply schemes by constructing pump house, community tank, laying of distribution pipeline for providing FHTC with supply, delivery and installation of pumping machineries & allied Electro-Mechanical accessories at Kanko G.P. in place of (Dharampur Zone-III Kanko (TSM/015873) and Dharampur Zone-II Barbasuli (TSM/015892) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | DIC(D)_MMSD(D) | Junior Engineer | ORD/000323/2023-2024 | 3016/JMD | 20/10/2023 | 17/02/2024 | MONDAL PRECISION PRIVATE LIMITED | 616.83 | 0 | 0 | 50
12 | JHARGRAM | Binpur - II | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS | SM/17929 | New | Servicing and repairing works of 6-CTA Engine with providing of spares attached with DTH CUM DR-500 Rig with others allied works of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Driller-In-Charge | Junior Engineer | ORD/001400/2023-2024 | 3082/JMD | 14/03/2024 | 29/03/2024 | RSA ENTERPRISE | 6.15 | 0 | 0 | 100
13 | JHARGRAM | Binpur - II | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS | SM/17929 | New | Material Requisition To Resource Division |  |  | RTOR000001/2023-2024 | 2867/JMD | 07/03/2024 |  | Resource Division | 4.8 | 0 | 0 | 0
Total | [13 empty] | 690.83 | 39.68 | 5.74