## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Division | AUGMENTATION OF POND WATER BASED BELPAHARI PIPE WATER SUPPLY SCHEME TO ACCOMMODATE FHTC AT BINPUR-II- BLOCKWITHIN JHARGRAM-DISTRICT, UNDER JHARGRAM DIVISION, PHE DTE. | SM/18428 | Augmentation | Construction of 600 Cum OHR(Intze type solid raft) ,Laying of Distribution ,clear Water & Raw Water Raising main to accommodate FHTC (7292 Nos) for Augmentation of Belpahari Water Supply Scheme within Binpur-II Block under Jhargram District under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer RWS, Binpur-II Devlopment Block. | ORD/000189/2023-2024 | 1463/JHD | 31/08/2023 | 27/02/2024 | M/S A.R ENTERPRISE | 929.37 | 216.88 | 23.34 | 70
2 | JHARGRAM |  | Jhargram Division | AUGMENTATION OF POND WATER BASED BELPAHARI PIPE WATER SUPPLY SCHEME TO ACCOMMODATE FHTC AT BINPUR-II- BLOCKWITHIN JHARGRAM-DISTRICT, UNDER JHARGRAM DIVISION, PHE DTE. | SM/18428 | Augmentation | Installation of 1000 Litres capacity PVC Water Tank and allied construction at Different Places under Belpahari W/S Scheme within Jhargram Sub-Division under Jhargram Division P.H.E.Dte. | Assistant Engineer | Junior Engineer-II | ORD/000345/2023-2024 | 966/JSD | 10/11/2023 | 01/12/2023 | SAIKAT DANDAPAT | 1.15 | 0.58 | 50 | 100
3 | JHARGRAM |  | Jhargram Division | AUGMENTATION OF POND WATER BASED BELPAHARI PIPE WATER SUPPLY SCHEME TO ACCOMMODATE FHTC AT BINPUR-II- BLOCKWITHIN JHARGRAM-DISTRICT, UNDER JHARGRAM DIVISION, PHE DTE. | SM/18428 | Augmentation | Laying of Pipe Line for uncovered habitation of Muransole Mouza under Belpahari WS Scheme within Binpur-II Block under Jhargram Division, P.H.E. Dte | Assistant Engineer | Junior Engineer-II | ORD/000346/2023-2024 | 967/JSD | 10/11/2023 | 01/12/2023 | SUNIL DULE | 3.07 | 1.54 | 50 | 100
4 | JHARGRAM |  | Jhargram Division | AUGMENTATION OF POND WATER BASED BELPAHARI PIPE WATER SUPPLY SCHEME TO ACCOMMODATE FHTC AT BINPUR-II- BLOCKWITHIN JHARGRAM-DISTRICT, UNDER JHARGRAM DIVISION, PHE DTE. | SM/18428 | Augmentation | Laying of Distribution Pipe Line due to damage in existing pipeline during Construction of Concrete Road from Merasuli to Sahari Rana Para & Adibasipara under Belpahari Water Supply Scheme. | Assistant Engineer | Junior Engineer-II | ORD/000434/2023-2024 | 148/JHD | 29/01/2024 | 13/02/2024 | SAIKAT DANDAPAT | 5.78 | 2.73 | 47.31 | 100
5 | JHARGRAM |  | Jhargram Division | AUGMENTATION OF POND WATER BASED BELPAHARI PIPE WATER SUPPLY SCHEME TO ACCOMMODATE FHTC AT BINPUR-II- BLOCKWITHIN JHARGRAM-DISTRICT, UNDER JHARGRAM DIVISION, PHE DTE. | SM/18428 | Augmentation | Continuation Work for Functional Household Tap Connection data uploading charges of different PWSS under Jhargram District in JJM_IMIS portal under Jal Jeevan Mission for 1st March 2024 to 15th March 2024 under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000697/2023-2024 | 451/JRWS | 27/02/2024 | 13/03/2024 | JAGOMOHAN SETUA | 0.63 | 0.31 | 49.79 | 100
6 | JHARGRAM |  | Jhargram Division | AUGMENTATION OF POND WATER BASED BELPAHARI PIPE WATER SUPPLY SCHEME TO ACCOMMODATE FHTC AT BINPUR-II- BLOCKWITHIN JHARGRAM-DISTRICT, UNDER JHARGRAM DIVISION, PHE DTE. | SM/18428 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000001/2024-2025 | 1094/JHD | 30/07/2024 |  | Resource Division | 184.4 | 0 | 0 | 0
7 | JHARGRAM |  | Jhargram Division | AUGMENTATION OF POND WATER BASED BELPAHARI PIPE WATER SUPPLY SCHEME TO ACCOMMODATE FHTC AT BINPUR-II- BLOCKWITHIN JHARGRAM-DISTRICT, UNDER JHARGRAM DIVISION, PHE DTE. | SM/18428 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000114/2023-2024 | 279/JHD | 20/02/2024 |  | Resource Division | 3.98 | 0 | 0 | 0
Total | [13 empty] | 1128.39 | 222.04 | 19.68