## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. | SM/18435 | Augmentation | Uncovered Habitation of Barasukjora Village under Augmentation of Barasukjora Pond Based Piped Water Supply Scheme (Zone-I) in Binpur-II Block within Jhargram Division under Jhargram Division P.H.E. Dte. (Phase - I) | Assistant Engineer | Junior Engineer-II | ORD/000034/2024-2025 | 739/JSD | 02/08/2024 | 23/08/2024 | ASSOCIATED ENGINEERS & TRADERS | 4.7 | 0 | 0 | 100
2 | JHARGRAM |  | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. | SM/18435 | Augmentation | Uncovered Habitation of Barasukjora Village under Augmentation of Barasukjora Pond Based Piped Water Supply Scheme (Zone-I) in Binpur-II Block within Jhargram Division under Jhargram Division P.H.E. Dte. (Phase - II) | Assistant Engineer | Junior Engineer-II | ORD/000035/2024-2025 | 740/JSD | 02/08/2024 | 23/08/2024 | ASSOCIATED ENGINEERS & TRADERS | 4.82 | 0 | 0 | 100
3 | JHARGRAM |  | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. | SM/18435 | Augmentation | Uncovered Habitation of Barasukjora Village under Augmentation of Barasukjora Pond Based Piped Water Supply Scheme (Zone-I) in Binpur-II Block within Jhargram Division under Jhargram Division P.H.E. Dte. (Phase - III) | Assistant Engineer | Junior Engineer-II | ORD/000036/2024-2025 | 741/JSD | 02/08/2024 | 23/08/2024 | ASSOCIATED ENGINEERS & TRADERS | 1.73 | 0 | 0 | 100
4 | JHARGRAM |  | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. | SM/18435 | Augmentation | Uncovered Habitation of Barasukjora Village under Augmentation of Barasukjora Pond Based Piped Water Supply Scheme (Zone-I) in Binpur-II Block within Jhargram Division under Jhargram Division P.H.E. Dte. (Phase - IV) | Assistant Engineer | Junior Engineer-II | ORD/000037/2024-2025 | 742/JSD | 02/08/2024 | 23/08/2024 | ASSOCIATED ENGINEERS & TRADERS | 4.67 | 0 | 0 | 100
5 | JHARGRAM |  | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. | SM/18435 | Augmentation | Laying of Distribution pipe line for Augmentation of Ground based Barasukjora Pond Based PWSS in Binpur-II with in Jhargram District under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000091/2023-2024 | 1143/JHD | 21/07/2023 | 20/08/2023 | SAIKAT DANDAPAT | 18.31 | 8.23 | 44.94 | 51
6 | JHARGRAM |  | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. | SM/18435 | Augmentation | Construction of OHR(200 Cum) and Soil Investigation for augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000141/2023-2024 | 1344/JHD | 10/08/2023 | 06/05/2024 | M.RAHAMAN CONSTRUCTION | 81.74 | 0 | 0 | 0
7 | JHARGRAM |  | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. | SM/18435 | Augmentation | Connection to Tail End Habitation from Clear Water Rising Main of Bamundiha Village under Augmentation of Barasukjora Pond Based Piped Water Supply Scheme (Zone-I) in Binpur-II Block within Jhargram District under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000347/2023-2024 | 969/JSD | 10/11/2023 | 01/12/2023 | SUNIL DULE | 3.79 | 1.75 | 46.21 | 100
8 | JHARGRAM |  | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. | SM/18435 | Augmentation | Repair, Renewing of existing water storage pond, Approach Road towards WTP also inspection Road round the pond embankment & Construction of Boundary wall on periphery of down stream toe wall cum guard wall of existing water storage pond under Augmentation of Barasukjora Surface water based P.W.S.S, Block: - Binpur - II, District: - Jhargram, under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000387/2023-2024 | 2009/JHD | 01/12/2023 | 29/04/2024 | GEE BEE NIRMAN CO. PRIVATE LIMITED | 1590.58 | 60.3 | 3.79 | 10
9 | JHARGRAM |  | Jhargram Division | Augmentation of Barasukjora Pond Based Water Supply Scheme within Jhargram District under Jhargram Division, P.H.E. Dte. | SM/18435 | Augmentation | Re-Laying of Distribution Line Orgonda to Biridanga Village (Orgonda Mouza) under Augmentation of Barasukjora Pond Based Piped Water Supply Scheme (Zone-II) in Binpur-II Block within Jhargram Division under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000435/2023-2024 | 149/JHD | 29/01/2024 | 13/02/2024 | SAIKAT DANDAPAT | 4.76 | 2.33 | 49.01 | 100
Total | [13 empty] | 1715.1 | 72.62 | 4.23