## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Mechanical Division | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATION AT ROHINI GROUND WATER BASED PIPED WATER SUPPLY SCHEME UNDER JJM PROGRAMME | SM/10289 |  | Supply, installation, testing & commissioning of sprinkler system facility for cleaning the installed solar panel with other allied works at Rohini piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000135/2024-2025 | 568/W/MMSD(D) | 04/07/2024 | 11/07/2024 | RSA ENTERPRISE | 0.5 | 0 | 0 | 0
2 | JHARGRAM |  | Jhargram Mechanical Division | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATION AT ROHINI GROUND WATER BASED PIPED WATER SUPPLY SCHEME UNDER JJM PROGRAMME | SM/10289 |  | Additional work in connection with providing solarisation of WBSEDCL Energised Pumping installation at Rohini Ground water Based piped Water supply Scheme under JJM Programme under Jhargram Mechanical Division, PHE Dte. | Assistant Engineer | JE (M) | ORD/000179/2023-2024 | 1962/JMD | 28/07/2023 | 04/08/2023 | DIPALI CONSTRUCTION | 0.19 | 0.19 | 100 | 100
3 | JHARGRAM |  | Jhargram Mechanical Division | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATION AT ROHINI GROUND WATER BASED PIPED WATER SUPPLY SCHEME UNDER JJM PROGRAMME | SM/10289 |  | Providing Solarizatin of WBSEDCL Energised Pumping installation at Rohini Ground water Based piped Water supply Scheme under JJM Programme under Jhargram Mechanical Division, PHE Dte. | Assistant Engineer | JE (M) | ORD/000424/2021-2022 | 339/JMD | 03/03/2022 | 02/04/2022 | DIPALI CONSTRUCTION | 6.17 | 2.43 | 39.31 | 100
Total | [13 empty] | 6.86 | 2.62 | 38.17