## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Mechanical Division | Providing solarization of WBSEDCL energised pumping installation at Rajband w/s scheme under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | SM/17079 |  | Providing solarization of WBSEDCL energised pumping installation at Pindrakuli and other w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | Assistant Engineer |  | ORD/000285/2023-2024 | 2502/JMD | 25/08/2023 | 21/02/2024 | SUBHASIS ROY | 31.3 | 0 | 0 | 0
Total | [13 empty] | 31.3 | 0 | 0