## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-II) PWSS. | SM/10640 | Augmentation | Acceptance cum work order for Construction of 150 cum capacity 20 mtr staging height RCC Over Head Reservoir (pipe connection and cost of pipes, specials at Augmentation of Jamuria Rural (Zone-II) Piped Water Supply Scheme under RCFA Division-I PHE Dte. (2nd Call) | Assistant Engineer 2 | Junior Engineer | ORD/000033/2023-2024 | 1631/RCD-I | 26/04/2023 | 20/04/2024 | UNITED CONSTRUCTION | 69.15 | 38.03 | 55 | 90
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-II) PWSS. | SM/10640 | Augmentation | Acceptance cum work order for Distribution network for Augmentation of Jamuria Rural- II Piped Water Supply Scheme including FHTC work (Segment- I) under Jamuria Block in the district of Paschim Bardhaman Under RCFA Division - I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000100/2024-2025 | 2120/RCD-I | 27/08/2024 | 26/10/2024 | SIMA ENTERPRISE | 46.06 | 0 | 0 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-II) PWSS. | SM/10640 | Augmentation | Acceptance cum work order for Distribution network for Augmentation of Jamuria Rural-II Piped Water Supply Scheme including FHTC work (Segment-III) under Jamuria Block in the the District of Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000112/2024-2025 | 2134/RCD-I | 27/08/2024 | 26/10/2024 | DAWN CONSTRUCTION | 95.92 | 0 | 0 | 0
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-II) PWSS. | SM/10640 | Augmentation | Acceptance cum work order for Distribution network for Augmentation of Jamuria Rural- II Piped Water Supply Scheme including FHTC work (Segment- II) under Jamuria Block in the district of Paschim Bardhaman under RCFA Division - I PHE Dte. | Assistant Engineer 2 |  | ORD/000118/2024-2025 | 2117/RCD-I | 27/08/2024 | 26/10/2024 | MS SAMANTA CONSTRUCTION | 48.54 | 0 | 0 | 0
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-II) PWSS. | SM/10640 | Augmentation | Preparation of DPR & Route Survey for Augmentation of Jamuria (Rural) (Zone-II) Piped Water Supply Scheme Block-Jamuria, Dist-Paschim Bardhaman under RCFA Division-I PHE Dte. (Sl No. 13) | Assistant Engineer 2 | Junior Engineer | ORD/000250/2022-2023 | 2230/RCD I | 15/09/2022 | 30/09/2022 | APEX ENGINEERING | 3.58 | 3.58 | 100 | 0
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-II) PWSS. | SM/10640 | Augmentation | Distribution network for Augmentation of Jamuria Rural-II Piped Water Scheme including FHTC work Block Jamuria, Dist Paschim Bardhaman under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000292/2022-2023 | 2449/RCD-I | 13/10/2022 | 11/04/2023 | JOY HIND TUBEWELLS | 236.71 | 29.64 | 12.52 | 100
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-II) PWSS. | SM/10640 | Augmentation | Sub Soil Investigation for 200 cum capacity RCC Over Head Reservoir of Jamuria Block for Augmentation of Jamuria Rural-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000524/2022-2023 | 3137/RCDI | 12/12/2022 | 19/12/2022 | P.K TEWARY DRILLING CO. | 0.55 | 0 | 0 | 0
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-II) PWSS. | SM/10640 | Augmentation | Acceptance cum work order for Construction of High Lift Pump House at Riverside H/W site under Augmentation of Jamuria Rural (Zone I & II) Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000573/2022-2023 | 3282/RCDI | 20/12/2022 | 20/03/2023 | GLOBAL CONSTRUCTION | 31.24 | 12.73 | 40.75 | 90
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-II) PWSS. | SM/10640 | Augmentation | Formal work order for augmentation of Jamuria (Rural)(zone-I) piped water supply scheme including FHTC & allied work within Jamuria Block under RCFA Div-I, PHE Dte.(Part-B) |  |  | ORD/000599/2022-2023 | 16/RCD I | 05/01/2023 | 04/02/2023 | DIP CONSTRUCTION | 0 | 0 | NAN | 0
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-II) PWSS. | SM/10640 | Augmentation | Acceptance cum Work Order for Rising Main of Augmentation of Jamuria Rural (Zone-I & II) under RCFA Division-I PHE Dte (sl.no-14) | Assistant Engineer 2 | Junior Engineer | ORD/000773/2022-2023 | 805/RCD-I | 06/03/2023 | 05/05/2023 | M/S MONDAL ENTERPRISE | 22.77 | 4.09 | 17.97 | 0
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-II) PWSS. | SM/10640 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000005/2022-2023 | 2345/RCD-I | 28/09/2022 |  | Resource Division | 9.24 | 0 | 0 | 0
Total | [13 empty] | 563.75 | 88.07 | 15.62