## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. | SM/10643 | Augmentation | Acceptance cum work order for Construction of 200 cum capacity 20 mtr. Staging height RCC Over Head Reservoir (pipe connection and cost of pipes, speciials at jamgram Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman. | Assistant Engineer 1 | Junior Engineer | ORD/000006/2023-2024 | 1403 RCD I | 12/04/2023 | 06/04/2024 | SRI KRISHNA ENTERPRISE | 72.48 | 57.98 | 80 | 90
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. | SM/10643 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of Jamgram Piped Water Supply Scheme Block Barabani, Dist- Paschim Bardhaman under RCFA Div-I PHE,Dte. (Part-B) | Assistant Engineer 1 | Junior Engineer | ORD/000097/2022-2023 | 1270/RCD-I | 02/06/2022 | 31/08/2022 | M/S S.K. ENTERPRISE | 24.81 | 23.46 | 94.56 | 80
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. | SM/10643 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of Jamgram Piped Water Supply Scheme Block Barabani, Dist- Paschim Bardhaman under RCFA Div-I PHE Dte. (Part-C) | Assistant Engineer 1 | Junior Engineer | ORD/000098/2022-2023 | 1271/RCD-I | 02/06/2022 | 31/08/2022 | ALOKESH BANERJEE | 23.92 | 23.08 | 96.51 | 80
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. | SM/10643 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of Jamgram Piped Water Supply Scheme Block Barabani, Dist- Paschim Bardhaman under RCFA Div-I PHE,Dte. (Part-D) | Assistant Engineer 1 | Junior Engineer | ORD/000099/2022-2023 | 1272/RCD-I | 02/06/2022 | 31/08/2022 | B.T.M CONCERN | 55.19 | 55.16 | 99.94 | 80
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. | SM/10643 | Augmentation | Acceptance cum work order Additional work for Distribution Network including adopting trench less technology at two places under Augmentation of Jamgram Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000216/2023-2024 | 2223/RCD-I | 17/07/2023 | 16/08/2023 | B.T.M CONCERN | 39.15 | 35.84 | 91.54 | 92
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. | SM/10643 | Augmentation | Acceptance cum work order Construction of Boundary wall including land development, approach road (Length-65 mtr) and drain (length-160 mtr) at Jamgram OHR site of Augmentation of Jamgram Piped Water Supply Scheme under Barabani Block under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000346/2023-2024 | 2479/RCD-I | 23/08/2023 | 22/09/2023 | SRI KRISHNA ENTERPRISE | 36.83 | 0 | 0 | 5
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. | SM/10643 | Augmentation | Acceptance cum work order Sinking of 4 (Four) nos river bed tube wells including collecting main & other allied works at Unionpara H/W under RCFA Part-II at Damodar river under Unionpara Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000349/2023-2024 | 2483/RCD-I | 23/08/2023 | 22/09/2023 | T.R. ENTERPRISE | 11.42 | 11.08 | 97 | 100
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. | SM/10643 | Augmentation | Providing FHTC through retrofitting under Augmentation of Jamgram PWSS (Part-I) under RCFA Div-I, PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000404/2022-2023 | 2519/RCDI | 20/10/2022 | 19/11/2022 | MAA ENTERPRISE | 22.6 | 5.52 | 24.44 | 60
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. | SM/10643 | Augmentation | Providing FHTC through retrofitting under Augmentation of Jamgram PWSS (Part-I) under RCFA Div-I, PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000405/2022-2023 | 2520/RCDI | 20/10/2022 | 19/11/2022 | B.T.M CONCERN | 50.77 | 11.03 | 21.72 | 65
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. | SM/10643 | Augmentation | Acceptance cum work order for Emergency Repairing of 750 mm dia Rising main with supply of leak repairing clamp and allied works related to supply of CI/DI specials etc, under Augmentation of Itapara Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000412/2023-2024 | 2612/RCD-I | 12/09/2023 | 02/10/2023 | MAKALI ENGINEERING CORPORATION | 98.81 | 98.81 | 100 | 100
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. | SM/10643 | Augmentation | Preparation of DPR for Augumentation of Jamgram Piped Water Supply Scheme Block - Barabani, Dist - Paschim Bardhaman under RCFA Division-I PHE Dte.(sl no 03) | Assistant Engineer 1 | Junior Engineer | ORD/000481/2021-2022 | 2347/RCD I | 17/12/2021 | 01/01/2022 | STEELCONC AND ASSOCIATES | 2.88 | 2.88 | 100 | 0
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. | SM/10643 | Augmentation | Sub Soil Investigation for 350 cum capacity RCC Over Head Reservoir of Jamuria Block for Augmentation of Jamuria Rural-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000525/2022-2023 | 3138/RCDI | 12/12/2022 | 19/12/2022 | P.K TEWARY DRILLING CO. | 0.55 | 0.27 | 50 | 100
13 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. | SM/10643 | Augmentation | Acceptance cum work order for rising Main for Augmentation of Jamgram Piped Water Supply Scheme at Baraboni Block Under RCFA - Div - I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000569/2022-2023 | 3278/RCD I | 20/12/2022 | 10/01/2023 | DEBI PRASAD MAJI | 15.63 | 11.07 | 70.86 | 100
14 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. | SM/10643 | Augmentation | Acceptance cum work order for Construction of Pump House at Jamgram for Augmentation of Jamgarm Piped Water Supply Scheme under RCFA, Division-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000570/2022-2023 | 3279/RCDI | 20/12/2022 | 03/02/2023 | R B ENTERPRISE | 20.73 | 14 | 67.54 | 90
15 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. | SM/10643 | Augmentation | Providing FHTC through retrofitting under Augmentation of Jamgram PWSS (Part-III) under RCFA Div-I, PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000606/2022-2023 | 3274/RCDI | 20/12/2022 | 19/01/2023 | M/S S.K. ENTERPRISE | 22.96 | 5.14 | 22.39 | 50
16 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. | SM/10643 | Augmentation | Additional work like Horizonal Augar boring, dismantaling concrete and allied works in releted to part-B of Augmentation of jamgram PWSS under RCFA division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000642/2023-2024 | 3394/RCD-I | 23/11/2023 | 30/11/2023 | M/S S.K. ENTERPRISE | 0.8 | 0.4 | 49.94 | 100
17 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. | SM/10643 | Augmentation | Acceptance cum work order for laying of HDPE Pipe line from Panuria Bazar to Shirikhad Para under Jamgram Panuria W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000646/2022-2023 | 344/RCD I | 30/01/2023 | 14/02/2023 | SHREE DURGA ENTERPRISE | 1.35 | 1.34 | 99.06 | 0
18 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. | SM/10643 | Augmentation | Acceptance cum work order for Additional work for laying 110 mm dia HDPE pipe with construction of piller for crossing a water body within Jamgram PWSS Part-C under Augmentation of Jamgram PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000674/2023-2024 | 3458/RCD-1 | 24/11/2023 | 09/12/2023 | ALOKESH BANERJEE | 3.39 | 1.26 | 37.33 | 100
19 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. | SM/10643 | Augmentation | Acceptance cum work order Ground Level Reservoir of capacity 105 cum for Augmentation Jamgram & its Adjoining Mouza Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000835/2022-2023 | 1062/RCD-I | 23/03/2023 | 19/09/2023 | SUBHADEEP DAS | 12.25 | 11.43 | 93.33 | 50
20 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. | SM/10643 | Augmentation | Acceptance cum work order Distribution Network for Augmentation of Jamgram Piped Water Supply Scheme including FHTC work Block Barabani, Dist-Paschim Bardhaman under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 2 | Junior Engineer | ORD/000960/2022-2023 | 1053/RCD-I | 23/03/2023 | 22/04/2023 | SRI KRISHNA ENTERPRISE | 90.22 | 34.13 | 37.83 | 55
21 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. | SM/10643 | Augmentation | Acceptance cum work order for Additional by constructing pillar for water body crossing including adopting trench less technology (e.g. Jack Pushing Method etc) at Three nos location including MS work and allied works related to rising main of Itapara and adjoining mouzas under Augmentation of Jamgram Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/001062/2023-2024 | 502/RCD-I | 12/02/2024 | 08/03/2024 | DURGA DAS MONDAL | 38.11 | 0.09 | 0.23 | 60
22 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. | SM/10643 | Augmentation | Acceptance cum Work Order for Laying of different dia HDPE pipeline Including other allied works at Khorabor, Rashunpur, Amuliya under Barabani Block of Jamgram Panuria PWSS under RCFA Div- I, PHE Dte. |  | Junior Engineer | ORD/001112/2023-2024 | 918/RCD-I | 15/03/2024 | 29/04/2024 | M/S B.K. CONSTRUCTION | 15.73 | 0 | 0 | 0
23 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. | SM/10643 | Augmentation | Acceptance cum Work Order for Construction of Switch room and balance work of approach road towards Gourbazar Head Works Site under Augmentation of Jamgram PWSS under RCFA Division-I PHE Dte | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/001115/2023-2024 | 921/RCD-I | 15/03/2024 | 14/05/2024 | R B ENTERPRISE | 8.42 | 4.13 | 49.02 | 100
24 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. | SM/10643 | Augmentation | Acceptance cum Work Order for Balance work of Laying distribution system within distribution network for Augmentation of Jamgram PWSS under RCFA Div- I, PHE Dte. (Part-D) | Assistant Engineer 1 | Junior Engineer | ORD/001121/2023-2024 | 927/RCD-I | 15/03/2024 | 29/04/2024 | B.T.M. CONCERN | 35.23 | 13.38 | 37.98 | 89
25 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamgram Piped Water Supply Scheme. | SM/10643 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000010/2022-2023 | 2350/RCD-I | 28/09/2022 |  | Resource Division | 12.32 | 0 | 0 | 0
26 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of Jamgram Piped Water Supply Scheme. | SM/10643 | Augmentation | New Connection at Jamgram Water Supply Scheme. |  |  | BILL/00170/2022-2023 | BP-2022-23-28 | 31/01/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.68 | 0 | 0 | 0
27 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of Jamgram Piped Water Supply Scheme. | SM/10643 | Augmentation | Providing & fitting, fixing of lighting luminaries, electrical wiring of pump house with yard lighting arrangement and other allied works at Gourbazar Pump House under Augmentation of Jamgram Piped Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000134/2024-2025 | 1319/AMD | 21/08/2024 | 05/10/2024 | INDUSTRIAL ELECTRICAL CORPORATION | 2.79 | 0 | 0 | 0
28 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of Jamgram Piped Water Supply Scheme. | SM/10643 | Augmentation | Supply, delivery & installation of Pumping Machineries and other Electro-Mechanical equipment at Jamgram Piped Water Supply Scheme under Asansol Mechanical Division, P.H.E Dte. Block- Barabani, District-Paschim Bardhaman. | Assistant Engineer-I | Junior Engineer-5 | ORD/000411/2022-2023 | 360/AMD | 09/02/2023 | 10/05/2023 | INDUSTRIAL ELECTRICAL CORPORATION | 46.39 | 28.18 | 60.73 | 95
29 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of Jamgram Piped Water Supply Scheme. | SM/10643 | Augmentation | Supply & installation of Sub-Mersible Pumping Machinery at RBTWs No-4, 5 and 6 of Ajoy at Jamgram Piped Water Supply Scheme, Block-Barabani, Dist.-Paschim Bardhaman. | Assistant Engineer-I | Junior Engineer-5 | ORD/000527/2023-2024 | 287/AMD | 20/02/2024 | 05/04/2024 | INDUSTRIAL ELECTRICAL CORPORATION | 8.4 | 0 | 0 | 72
Total | [13 empty] | 776.8 | 449.67 | 57.89